## Sheet2
TaskID | Sub Team | Resp Function | Resp Person | PACE | LP | Task Name | Duration | Start | Finish | Predecessors | Successors | Scope Definition (Arnab) | Current SIMPL Phase (visibility) | VoS (visibility) | Commercial/Technical Lego Block | Lego Block (Arnab) | Body of Evidence (both - Arnab - 1) | Bucket of Work (visibility - old)
18 | All | IDM | MADs |  |  | XX Country Sales Samples Due to "Company Issuing Sales Samples to Trade" (date needed) | 0d | Tue 11/10/26 | Tue 11/10/26 | 1004 | 21 | Sales Samples | Launch |  | Technical Scope | Mandatory
19 | All | IDM | MADs |  |  | XX Country Sales Samples Due to "Company Issuing Sales Samples to Trade" (date needed) | 0d | Tue 11/10/26 | Tue 11/10/26 | 1004 | 22 | Sales Samples | Launch |  | Technical Scope | Mandatory
20 | All | IDM | MADs |  |  | XX Country Sales Samples (date needed) | 0d | Tue 11/10/26 | Tue 11/10/26 | 1004 | 23 | Sales Samples | Launch |  | Technical Scope | Mandatory
21 | All | Sales | Sales | A |  | Initiative or Bundle Release to Trade (date needed) | 0d | Fri 4/25/31 | Fri 4/25/31 | 7,18,679,694 | 25,22FS+10d | SOS Dates | Launch |  | All | Mandatory
22 | All | Sales | Sales | A |  | Separate Country Release to Trade (date needed) | 0d | Fri 5/9/31 | Fri 5/9/31 | 19,21FS+10d | 25,24 | SOS Dates | Launch |  | Technical Scope | Mandatory
23 | All | Sales | Sales | A |  | Separate Country Release to Trade (date needed) | 0d | Fri 4/25/31 | Fri 4/25/31 | 7,20 | 8FS+4mo,26 | SOS Dates | Launch |  | Technical Scope | Mandatory
24 | Supply | MLL | MLL |  |  | Country XX Customer Notification Deadline for Direct Store Delivery (date needed) | 3w | Fri 5/9/31 | Fri 5/30/31 | 22 | 913 | SOS Dates | Launch |  | Technical Scope | Mandatory
25 | All | SNO | IOL |  |  | First Order Date Country XX (date required) | 0d | Fri 5/9/31 | Fri 5/9/31 | 21,22 | 27FS+4w | SOS Dates | Launch |  | Technical Scope | Mandatory
26 | Supply | MLL | MLL/MIL |  |  | Country XX Customer Notification Deadline for Direct Store Delivery (date needed) | 6d | Fri 4/25/31 | Mon 5/5/31 | 23 | 913 | SOS Dates | Launch |  | Technical Scope | Mandatory
27 | All | SNO | IOL |  |  | Last Order Date for First Delivery Date (date required) | 0d | Fri 6/6/31 | Fri 6/6/31 | 25FS+4w |  | SOS Dates | Launch |  | Technical Scope | Mandatory
28 | All | SNO | IOL |  |  | First Delivery Date (date set) | 0d | Tue 5/6/31 | Tue 5/6/31 | 29FS-2w | 1053FS-9w | SOS Dates | Launch |  | Technical Scope | Mandatory
29 | All | SNO | IOL |  |  | Start of Shipments (Country XX) (date set) | 0d | Tue 5/20/31 | Tue 5/20/31 | 161081 | 28FS-2w,30FS+3d | SOS Dates | Launch |  | Technical Scope | Mandatory
30 | All | SNO | IOL |  |  | Start of Shipments (Country XX) (date set) | 0d | Fri 5/23/31 | Fri 5/23/31 | 29FS+3d | 31 | SOS Dates | Launch |  | Technical Scope | Mandatory
31 | All | SNO | IOL |  |  | Start of Shipments (Country XX) (date set) | 0d | Fri 5/23/31 | Fri 5/23/31 | 30 |  | SOS Dates | Launch |  | Technical Scope | Mandatory
33 | Tech | Eng | Eng | A |  | Prelim Funding for Any Relevant equipment with long lead times | 0d | Wed 5/27/26 | Wed 5/27/26 | 139 | 633FS+3mo | Eng Scope | Discover |  | Technical Scope | Capital Funding
35 | Tech | Eng | Eng |  |  | Funding Booklet Completion - Partial | 0d | Thu 11/18/27 | Thu 11/18/27 | 5FS-16w | 36 | Eng Scope | Design |  | Technical Scope | Capital Funding
36 | Tech | Eng | Eng | A |  | Capital Concurrence for Partial (note approver here) | 1d | Thu 11/18/27 | Fri 11/19/27 | 35 | 37 | Eng Scope | Design |  | Technical Scope | Capital Funding
37 | Tech | Eng | Eng | A |  | Engineering Concurrence for Partial (note approvers here) | 1d | Fri 11/19/27 | Mon 11/22/27 | 36 | 38 | Eng Scope | Design |  | Technical Scope | Capital Funding
38 | Tech | Eng | Eng |  |  | Final Memo & ROAuthorization in STEAM for Partial | 1d | Mon 11/22/27 | Tue 11/23/27 | 37 | 39 | Eng Scope | Design |  | Technical Scope | Capital Funding
39 | Tech | Eng | Eng | A |  | STEAM Approval Partial Appropriation | 1w | Tue 11/23/27 | Tue 11/30/27 | 38 | 40 | Eng Scope | Design |  | Technical Scope | Capital Funding
40 | Tech | Eng | Eng | A |  | Partial Funding Purchase Order Ready | 1d | Tue 11/30/27 | Wed 12/1/27 | 39 | 836 | Eng Scope | Design |  | Technical Scope | Capital Funding
42 | Tech | Eng | Eng |  |  | Funding Booklet Completion - Final Appropriation | 2d | Tue 12/7/27 | Wed 12/8/27 | 639SS | 43 | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
43 | Tech | Eng | Eng | A |  | Capital Concurrence Final Appropriation (note approver here) | 1d | Thu 12/9/27 | Thu 12/9/27 | 42 | 44 | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
44 | Tech | Eng | Eng | A |  | Engineering Concurrence Final Appropriation (note approvers here) | 1d | Fri 12/10/27 | Fri 12/10/27 | 43 | 45 | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
45 | Tech | Eng | Eng |  |  | Final Memo & ROAuthorization in STEAM for Final Appropriation | 1d | Mon 12/13/27 | Mon 12/13/27 | 44 | 46 | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
46 | Tech | Eng | Eng | A |  | STEAM Approval Final Appropriation | 2d | Tue 12/14/27 | Wed 12/15/27 | 45 | 47 | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
47 | Tech | Eng | Eng | A |  | Final Funding Purchase Order Ready | 2w | Thu 12/16/27 | Wed 12/29/27 | 46 |  | Eng Scope | Qualify & Ready |  | Technical Scope | Capital Funding
48 | Tech | Global | Global |  | LP | Concept test - Idea Hamper (incl key visual) | 2mo | Mon 11/3/25 | Thu 1/1/26 |  | 120,121,141,142,143,64,49,109 | Commercial Concept/Sell-in, New Claim | Define |  | Commercial Facing | Mandatory | Ready to Kickoff | Kickoff Brief
49 | Comm | A&I | A&I |  |  | Strategic Target Consumer Defined and Confirmed | 5d | Fri 1/2/26 | Thu 1/8/26 | 48 | 50SS,51SS,52SS,53SS,166 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: MNI: P2P
50 | Comm | A&I | A&I |  |  | Prime Prospect Holistic Profile including receptivity insights | 5d | Fri 1/2/26 | Thu 1/8/26 | 49SS | 64166 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: MNI: P2P
51 | Comm | A&I | A&I |  |  | Consumer Needs, Barriers to trial, Shopper needs, | 5d | Fri 1/2/26 | Thu 1/8/26 | 49SS | 64166 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: MNI: P2P
52 | Comm | A&I | A&I |  |  | Purchase barriers, channel preferences, and Point of Market Entry (POME) | 5d | Fri 1/2/26 | Thu 1/8/26 | 49SS | 64166 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: MNI: P2P
53 | Comm | A&I | A&I |  |  | Why target consumer is attractive for customer | 5d | Fri 1/2/26 | Thu 1/8/26 | 49SS | 64166 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: MNI: P2P
54 | All | Sales | Sales |  |  | Confirm Brand Safari in last 6 months and shelf vision in place | 0d | Mon 11/3/25 | Mon 11/3/25 |  | 64,55,56,60,167 | Commercial Concept/Sell-In | Define |  | Commercial Facing | Package, Artwork, Formula | Ready to Kickoff | Kickoff Brief
55 | All | Sales | Sales |  |  | Define Potential conversion strategy | 5d | Mon 11/3/25 | Fri 11/7/25 | 54 | 64,62,61,172 | All | Define |  | Technical Scope | Mandatory | Ready to Kickoff | Kickoff Brief
56 | All | Sales | Marketing, Sales |  |  | Define potential brands, skus, forms, countries markets | 1w | Mon 11/3/25 | Fri 11/7/25 | 54 | 64,61,160,161,162 | All | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
57 | All | Mktg | Mktg |  |  | Define initial value proposition for the company (iNOS, volume) | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 143,142,144,61 | All | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
58 | All | R&D | PR |  |  | Define potential package and formula requirements (incl Sustainability) | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 120,64,62,61,117,137,146,147,148,149,89,118,119,122,121 | All | Define |  | Technical Scope | Mandatory | Ready to Kickoff | Kickoff Brief
59 | All | SNO | SCL |  |  | Define potential supply chain requirements | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 64,62,61,117 | All | Define |  | Technical Scope | Mandatory | Ready to Kickoff | Kickoff Brief
60 | All | Sales | Marketing, Sales |  |  | Define potential pricing/margins/category growth plan | 1w | Mon 11/3/25 | Fri 11/7/25 | 54 | 64,61 | Commercial Concept/Sell-In | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
61 | All | IDM | IL |  |  | Define Potential Risk & Assumptions (LOFAs - Leap of Faith Assumptions) | 1w | Mon 11/10/25 | Fri 11/14/25 | 55,56,57,58,59,60 | 64582 | All | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
62 | All | IDM | IL |  |  | Schedule Drafted with Learning Plan Suggestion | 1w | Mon 11/10/25 | Fri 11/14/25 | 55,58,59 | 64,63 | Commercial Concept/Sell-In | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
63 | Comm | A&I | A&I | A |  | A&I Learning Plan Drafted | 1w | Mon 11/17/25 | Fri 11/21/25 | 62 | 64 | Commercial Concept/Sell-in, New Claim | Discover |  | Commercial Facing | Package, Artwork, Formula | Ready to Learn/Design | Commercial Readiness
64 | All | IDM | IL | A |  | Brief Approved - Project Kicked Off | 1d | Fri 1/9/26 | Fri 1/9/26 | 55,56,58,59,60,61,48,54,62,63,50,51,52,53 | 68,66,3,72,113 | All | Define |  | All | Mandatory | Ready to Kickoff | Kickoff Brief
66 | All | SNO | IOL |  |  | SKU ID'ed (including ecommerce) | 2w | Fri 3/13/26 | Thu 3/26/26 | 206,64,81 | 163172103 | All | Discover |  | Commercial Facing | Mandatory | Ready to Learn/Design | Market Readiness
68 | Comm | Sales | Sales |  |  | Bundling Principles confirmed with Bundle Sales Leader (confirm if this project should be bundled with others) | 1w | Mon 1/12/26 | Fri 1/16/26 | 64 | 69 | Commercial Concept/Sell-In | Discover |  | All | Mandatory |  | Market Readiness
69 | Comm | Sales | Sales |  |  | Bundling risks & assumptions with Bundle Sales Ldr | 2w | Mon 1/19/26 | Fri 1/30/26 | 68 | 70174 | Commercial Concept/Sell-In | Discover |  | Commercial Facing | Mandatory |  | Market Readiness
70 | Comm | Sales | Sales | A |  | Where to play confirmed - ecommerce, channels? | 1w | Mon 2/2/26 | Fri 2/6/26 | 69 | 88167 | Commercial Concept/Sell-In | Discover |  | Commercial Facing | Mandatory |  | Market Readiness
72 | Comm | Mktg | Mktg |  |  | Ideation on Concepts and Claims | 2d | Mon 1/12/26 | Tue 1/13/26 | 64 | 73 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: Concept
73 | Comm | PR | PR |  |  | Claims Screener | 2d | Wed 1/14/26 | Thu 1/15/26 | 72 | 74,75 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: Concept
74 | Comm | Mktg | Mktg | A |  | Concept Iterations with GM Lead Team/Lead Mktg Agency Reps | 1d | Fri 1/16/26 | Fri 1/16/26 | 73 | 76 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Concept
75 | Comm | PR | PR | A |  | Legal Submission on Claims/Concepts | 1d | Fri 1/16/26 | Fri 1/16/26 | 73 | 77 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: Concept
76 | Comm | A&I | A&I |  |  | Concepts Washboard | 2d | Mon 1/19/26 | Tue 1/20/26 | 74 | 78 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Concept
77 | Comm | PR/Mktg | PR/Mktg | A |  | Legal Approval of Claims/Concepts | 2d | Mon 1/19/26 | Tue 1/20/26 | 75 | 348211 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: Concept
78 | Comm | Mktg | Mktg | A |  | Final Approval with GM before Concept Evaluator | 1d | Wed 1/21/26 | Wed 1/21/26 | 76 | 79 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Concept
79 | Comm | A&I | A&I |  |  | Concept Evaluator | 5w | Thu 1/22/26 | Tue 3/10/26 | 78 | 80 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Concept
80 | Comm | A&I | A&I |  |  | Compile Results and Share | 2d | Wed 3/11/26 | Thu 3/12/26 | 79 | 81 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Concept
81 | Comm | Mktg | Mktg | A |  | Approval of Final Concept for use in A&I Learning Plan | 0d | Thu 3/12/26 | Thu 3/12/26 | 80 | 89,90,84,91,92,96,66 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory | Ready to Learn/Design | CR: Concept
84 | Comm | Mktg | Mktg |  |  | Update concepts to include any other relevant impacted brands/forms | 35d | Fri 3/13/26 | Fri 5/1/26 | 81 | 85,86 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | CR: MNI: Creative
85 | Comm | A&I | A&I |  |  | Concept Screener to include any other relevant impacted brands/forms | 25d | Mon 5/4/26 | Mon 6/8/26 | 84 |  | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | CR: MNI: Creative
86 | Tech | PR | PR |  |  | Confirm Claims on reco'd concepts | 5d | Mon 5/4/26 | Fri 5/8/26 | 84 | 87396 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Package, Artwork, Formula |  | CR: MNI: Creative
87 | Comm | Mktg | Mktg | A | LP | Concept approved for Virtual Launch | 0d | Fri 5/8/26 | Fri 5/8/26 | 86 | 396 | Commercial Concept/Sell-In | Design |  | Commercial Facing | LP: Virtual Launch |  | CR: MNI: Creative
88 | Comm | Sales | Sales | A |  | CVA MRAT (customer value assessment, Market Readiness assessment tool) | 1w | Mon 2/9/26 | Fri 2/13/26 | 70 | 193582583167170 | Commercial Concept/Sell-in | Define |  | Commercial Facing | Mandatory | Ready to Learn/Design | Value, Commercial Readiness
89 | Comm | A&I | A&I |  |  | TPA Drafted (Trial Potential Assessment) | 1w | Fri 3/13/26 | Thu 3/19/26 | 81,58 | 208582583 | Commercial Concept/Sell-in | Discover |  | Commercial Facing | Package, Artwork, Formula | Ready to Learn/Design | Commercial Readiness
90 | Comm | Mktg | Mktg |  |  | Claims summary drafted | 2w | Fri 3/13/26 | Fri 3/27/26 | 81 | 99211 | Commercial Concept/Sell-in, New Claim | Discover |  | Commercial Facing | Claims |  | Commercial Readiness
91 | Comm | Mktg | Mktg |  |  | Update Claims for any variants that need to change based on work to date | 12d | Fri 3/13/26 | Mon 3/30/26 | 81 | 93370 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Claims |  | Commercial Readiness
92 | Comm | Mktg | Mktg |  |  | Update Verbatims from Concept | 12d | Fri 3/13/26 | Mon 3/30/26 | 81 | 93 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Claims |  | Commercial Readiness
93 | Comm | Mktg | Mktg |  |  | Review claims chgs with legal and do small technical testing for high risk areas | 4d | Tue 3/31/26 | Fri 4/3/26 | 91,92 | 94 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Claims |  | Commercial Readiness
94 | Comm | Mktg | Mktg |  |  | Place concept in test to confirm partiy | 9d | Mon 4/6/26 | Thu 4/16/26 | 93 | 95 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Commercial Readiness
95 | Comm | Mktg | Mktg | A |  | Approval of new updated concept to move forward | 1d | Fri 4/17/26 | Fri 4/17/26 | 94 | 97496 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Commercial Readiness
96 | Comm | Mktg | Mktg |  |  | Creative/Communication brief development | 22d | Fri 3/13/26 | Mon 4/13/26 | 81 | 97 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Commercial Readiness
97 | Comm | Mktg | Mktg | A |  | Creative/Communication Brief approval | 0d | Fri 4/17/26 | Fri 4/17/26 | 95,96 | 196,99,151 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory | Ready to Learn/Design | Commercial Readiness
99 | Comm | Design | Design |  |  | Create Design Brief with Mktg and CMK | 5d | Mon 7/20/26 | Fri 7/24/26 | 90,156,97 | 100 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
100 | Comm | Design | Design | A |  | Design Brief Approved | 1d | Mon 7/27/26 | Mon 7/27/26 | 99 | 101 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
101 | Comm | Design | Design |  |  | Kickoff Meeting with agency | 1d | Tue 7/28/26 | Tue 7/28/26 | 100 | 102 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
102 | Comm | Design | Design |  |  | Design Estimate received from agency | 1d | Wed 7/29/26 | Wed 7/29/26 | 101 | 103 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
103 | Comm | Design | Design |  |  | Establish brand codes and Pieces of Art (POA)s needed | 1d | Thu 7/30/26 | Thu 7/30/26 | 102,66 | 104 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
104 | Comm | Design | Design | A |  | Design Estimate approved | 1d | Fri 7/31/26 | Fri 7/31/26 | 103 | 105 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
105 | Comm | Design | Design |  |  | Purchase Order opened to agency | 1d | Mon 8/3/26 | Mon 8/3/26 | 104 | 106 | New Artwork | Discover |  | Commercial Facing | Artwork |  | CR: Artwork
106 | Comm | Design | Design |  |  | Prelim. dyelines sent to agency | 2d | Tue 8/4/26 | Wed 8/5/26 | 105 | 287 | New Artwork | Discover |  | Commercial Facing | Artwork | Ready to Learn/Design | CR: Artwork
109 | Tech | Process | Process |  | LP | C&U make products (list variants and month needed) | 30d | Fri 1/2/26 | Thu 2/12/26 | 48 | 110FS+2d,111 | New Formula | Design |  | Technical Scope | LP: C&U |  | LP: C&U
110 | Tech | PR | Russ |  | LP | Fill C&U product | 2w | Tue 2/17/26 | Mon 3/2/26 | 109FS+2d | 111 | New Formula | Design |  | Technical Scope | LP: C&U |  | LP: C&U
111 | Tech | PR | PR |  | LP | Place C&U micro test & results | 9.5w | Tue 3/3/26 | Mon 5/25/26 | 109110 | 122141142143587 | New Formula | Design |  | Technical Scope | LP: C&U |  | LP: C&U
113 | Tech | Pkg Dev | MPD |  |  | Intellectual Property Position/Patent (Freedom To Practice Search) | 2w | Mon 1/12/26 | Fri 1/23/26 | 64 | 114 | All | Discover |  | All | Mandatory |  | TR: Intellectual Property
114 | Tech | Pkg Dev | MPD | A |  | Determine Intellectual Property (IP) Strategy | 2w | Mon 1/26/26 | Fri 2/6/26 | 113 | 115,573,581SS,571 | All | Discover |  | All | Mandatory |  | TR: Intellectual Property
115 | Tech | Mktg | Mktg |  |  | Patent design Trademark application submitted, if applicable | 2w | Mon 2/9/26 | Fri 2/20/26 | 114 | 116 | All | Discover |  | All | Mandatory |  | TR: Intellectual Property
116 | Tech | Pkg Dev | MPD |  |  | Intellectual Property (IP) index | 5d | Mon 2/23/26 | Fri 2/27/26 | 115 | 680 | All | Discover |  | All | Mandatory | Ready to Learn/Design | TR: Intellectual Property
117 | Tech | IDM | Shelly/Tom |  |  | Connect & Develop due diligence w/sites | 2w | Mon 11/10/25 | Fri 11/21/25 | 58,59 | 138118119120 | All | Discover |  | Technical Scope | Package, Formula, Equipment | Ready to Learn/Design | Technical Readiness
118 | Tech | PD | Process/MPD |  |  | Product & Package TFS draft | 1w | Mon 11/24/25 | Fri 11/28/25 | 58117 | 141574120 | All | Discover |  | Technical Scope | Package, Formula, Equipment |  | Technical Readiness
119 | Tech | Eng | Eng |  |  | Process flow sheet draft | 1w | Mon 11/24/25 | Fri 11/28/25 | 58117 | 141576120 | All | Discover |  | Technical Scope | Package, Formula, Equipment |  | Technical Readiness
120 | Tech | Process | Process |  |  | Technical Learning Plan ID'ed | 2w | Mon 6/15/26 | Thu 7/9/26 | 48,148,149,58,122,117,118,119,146 | 583587 | All | Discover |  | Technical Scope | Package, Formula, Equipment | Ready for Early Capital | Technical Readiness
121 | Tech | PR | PR |  |  | Draft QEC I | 2w | Wed 7/1/26 | Fri 7/17/26 | 48,201,58,146 | 575587 | All | Discover |  | Technical Scope | Package, Formula, Equipment | Ready for Early Capital | Technical Readiness
122 | Tech | Global | Global |  |  | Supply Network Capacity Analysis (Mat'l & Dist., New Supplier Confirmation) | 3w | Mon 5/25/26 | Mon 6/15/26 | 58111 | 4.6416e+18 | All | Discover |  | Technical Scope | Supply Network | Ready for Early Capital | Technical Readiness
124 | Tech | Pkg Dev | MPD |  |  | Design Intent Approval (DIA) draft | 1w | Thu 12/11/25 | Wed 12/17/25 | 146147 | 125 | New Package | Discover |  | Technical Scope | Package |  | TR: Package DIA
125 | Tech | Pkg Dev | MPD |  |  | Design Intent Approval (DIA) review | 4w | Thu 12/18/25 | Wed 1/14/26 | 124 | 126 | New Package | Discover |  | Technical Scope | Package |  | TR: Package DIA
126 | Tech | Pkg Dev | MPD | A |  | Design Intent Approved (DIA) | 1w | Thu 1/15/26 | Thu 1/22/26 | 125 | 610FS+1w,128 | New Package | Discover |  | Technical Scope | Package |  | TR: Package DIA
128 | Tech | Pkg Dev | MPD |  |  | Build 3D files | 3d | Fri 1/23/26 | Tue 1/27/26 | 126 | 129 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
129 | Tech | Pkg Dev | MPD |  |  | Prototyping | 1d | Wed 1/28/26 | Wed 1/28/26 | 128 | 130 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
130 | Tech | Pkg Dev | MPD |  | LP | Consumer test | 1d | Thu 1/29/26 | Thu 1/29/26 | 129 | 131 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
131 | Tech | Pkg Dev | MPD |  |  | Prelim design locked | 1d | Fri 1/30/26 | Fri 1/30/26 | 130 | 132133 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
132 | Tech | Pkg Dev | MPD |  |  | Should cost / feasibility | 4d | Mon 2/2/26 | Thu 2/5/26 | 131 | 144 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
133 | Tech | Pkg Dev | MPD |  |  | Develop 3D with mold builder (or pkg machine development - depending on assembled or formulated business) | 19d | Mon 2/2/26 | Fri 2/27/26 | 131 | 134 | New Package | Discover |  | Technical Scope | Package |  | TR: DIA: Design Package
134 | Tech | Pkg Dev | MPD | A |  | DIA review and approval | 2w | Mon 3/2/26 | Fri 3/13/26 | 133 | 135 | New Package | Discover |  | Technical Scope | Package |  | TR: Package DIA
135 | Tech | Pkg Dev | MPD |  |  | DIA Final | 0d | Fri 3/13/26 | Fri 3/13/26 | 134 | 136 | New Package | Discover |  | Technical Scope | Package |  | TR: Package DIA
136 | Tech | Pkg Dev | MPD | A |  | Funding approval | 2w | Mon 3/16/26 | Fri 3/27/26 | 135 | 139,5 | New Package | Discover |  | Technical Scope | Package | Ready for Early Capital/Ready to Invest | TR: Package DIA
137 | Tech | Eng | Eng |  |  | Front End Engineering (FEI) work graduated | 1d | Mon 11/10/25 | Mon 11/10/25 | 58 | 138,139,4 | FEI | Discover |  | Technical Scope | Package, Formula, Equipment, Supply Network | Ready to Learn | Technical Readiness
138 | Tech | Eng. | Eng |  |  | Manufacturing Readiness Defined (All plts/CMs) | 22d | Mon 11/24/25 | Wed 12/24/25 | 137117 | 139,5 | Production & Distribution, Customization | Discover |  | Technical Scope | Package, Formula, Equipment, Supply Network | Ready for Early Capital/Ready to Invest | Technical Readiness
139 | Tech | Eng. | Eng |  |  | Engineering Prelim Concurrence | 42d | Mon 3/30/26 | Wed 5/27/26 | 138136137 | 144,33,141 | Eng Scope | Discover |  | Technical Scope | Package, Formula, Equipment, Supply Network | Ready for Early Capital | Technical Readiness
141 | All | Global | Global |  |  | Country Total Delivered Cost (TDC) test complete | 1mo | Thu 5/28/26 | Fri 6/26/26 | 118,119,48,146,139,111 | 144 | All | Discover |  | Technical Scope | Mandatory |  | Financials
142 | All | A&I | A&I | A |  | Volume locked | 2mo | Mon 5/25/26 | Tue 9/1/26 | 48,57,111 |  | All | Discover |  | All | Mandatory | Ready to Learn | Financials
143 | All | A&I | A&I |  |  | Cannibalization locked | 2mo | Mon 5/25/26 | Thu 9/3/26 | 48,57,111 |  | All | Discover |  | Commercial Facing | Mandatory | Ready to Learn | Financials
144 | All | Global | Global | A |  | Cost estimated (capital/formula/etc.) | 1mo | Mon 6/29/26 | Mon 11/16/26 | 141,148,149,132,57,139 | 5 | All | Discover |  | Technical Scope | Package, Artwork, Formula | Ready for Early Capital/Ready to Commit/Invest | Financials
146 | All | Global | Global |  |  | Studies (if applicable) | 1mo | Mon 11/10/25 | Wed 12/10/25 | 58 | 141124120121 | All | Discover |  | Technical Scope | Mandatory |  | Project Specific
147 | All | Global | Global |  |  | FMOT assessments | 1mo | Mon 11/10/25 | Wed 12/10/25 | 58 | 124 | New Artwork, New Package, New Brand Architecture, New Price | Discover |  | Commercial Facing | Brand Architecture |  | Project Specific
148 | All | Mktg/Eng./PR | Brooke/Eng/PR |  |  | Mfg strategy options evaluated | 1mo | Mon 11/10/25 | Wed 12/10/25 | 58 | 144120 | Production & Distribution, Customization, SND Scope | Discover |  | Technical Scope | Mandatory | Ready for Early Capital | Project Specific
149 | All | Eng./Mktg | Eng/Mktg |  |  | Capacity constraints (Mfg/Customer) evaluated and resolved | 1mo | Mon 11/10/25 | Wed 12/10/25 | 58 | 144120 | Production & Distribution, Customization, SND Scope | Discover |  | Technical Scope | Mandatory | Ready for Early Capital | Project Specific
151 | All | Design | Design | A |  | Brand Architecture Approved (clustering, brand stretch) | 5d | Mon 4/20/26 | Fri 4/24/26 | 97 | 152 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
152 | All | Design | Design |  |  | Brand Vision Development - bringing the architecture to life | 1mo | Mon 4/27/26 | Wed 5/27/26 | 151 | 155153287 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
153 | All | Design | Design |  |  | Testing on Brand Vision | 10d | Thu 5/28/26 | Wed 6/10/26 | 152 | 154 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
154 | All | Design | Design | A |  | Approved Brand Vision (incl Quall feedback and iterations) | 1d | Thu 6/11/26 | Thu 6/11/26 | 153 | 155 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
155 | All | Design | Design |  |  | Kickoff Package Design | 3d | Fri 6/12/26 | Tue 6/16/26 | 152154 | 156 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
156 | All | Design | Design |  |  | 2D Development | 1mo | Wed 6/17/26 | Fri 7/17/26 | 155 | 157,99,394 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
157 | All | Design | Design |  |  | Qualitative on 2D Design | 2w | Mon 7/20/26 | Fri 7/31/26 | 156 | 287 | New Brand Architecture | Discover |  | Commercial Facing | Brand Architecture |  | Brand Architecture
160 | All | IDM | IL |  |  | Request Country XX brand code incl. Trays/Customization Needs | 2w | Mon 11/10/25 | Fri 11/21/25 | 56 | 749682163 | All | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
161 | All | IDM | IL |  |  | Request Country XX brand code incl. trays/Customization Needs | 2w | Mon 11/10/25 | Fri 11/21/25 | 56 | 749682163 | All | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
162 | All | IDM | IL |  |  | Request Country XX brand codes incl. trays/Customization Needs | 2w | Mon 11/10/25 | Fri 11/21/25 | 56 | 749682163 | All | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
163 | All | SNO | Joel | A |  | SKUs Locked (sizes, forms, channels) | 2w | Tue 3/14/28 | Mon 3/27/28 | 583,66,172,160,161,162,647 | 190SS,164 | All | Design |  | All | Mandatory |  | Market Readiness
164 | All | SNO | IOL |  |  | Brand codes with Active Projected SKU List application into DSBP | 1w | Tue 3/28/28 | Mon 4/3/28 | 163 | 748 | All | Design |  | All | Mandatory |  | Market Readiness
166 | Comm | Sales/Finance | Sales/Finance | A |  | Pricing & Sizing Strategy: Rationale Including Competitive Benchmarking, Customer Differentiation | 2w | Thu 9/3/26 | Wed 9/16/26 | 401,49,50,51,52,53 | 659168 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
167 | Comm | Sales | Sales | A |  | Lock Shelving Strategy | 1w | Mon 2/16/26 | Mon 2/23/26 | 54,70,88 | 168206683 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Customer Selling
168 | Comm | Sales | Sales |  |  | Refine Preliminary customer selling strategy (Floor Price Minimum, Recommended Pricing) | 3d | Thu 9/17/26 | Mon 9/21/26 | 167,166,405FS-2w | 170,169SS,680,180,181,182,183,184,185,174,175,176,177,178,190,191 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Customer Selling
169 | Comm | IDM | Sales/IDM | A |  | Identify Sales Samples needs/production strategy | 1w | Thu 9/17/26 | Wed 9/23/26 | 168SS | 999 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
170 | Comm | Sales | Sales | A |  | Customer plans locked (Distribution Shelving merch) | 3d | Tue 9/22/26 | Thu 9/24/26 | 168,88 | 171187271186 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Customer Selling
171 | Comm | Sales | Sales |  |  | Lock Distribution Priorities | 3d | Fri 9/25/26 | Tue 9/29/26 | 170 | 682SS | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Customer Selling
172 | All | Sales | Sales | A |  | Lock if hard or soft conversion | 1d | Fri 3/27/26 | Fri 3/27/26 | 55,66 | 1.6318e+17 | All | Design |  | Commercial Facing | Package, Artwork, Formula |  | Market Readiness
174 | Comm | SNO | MLL/MIL |  |  | Lock Bundle Display line-up (incl pricing strategy within the bundle) | 6d | Tue 9/22/26 | Tue 9/29/26 | 168,401,69 | 861188 | All | Design |  | All | Mandatory |  | MR: Cust Sellin: Merch
175 | Comm | SNO | MLL/MIL |  |  | Lock notification date / strategy for display launch | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Merch
176 | Comm | SNO | MLL/MIL |  |  | Lock current Customization / Display simplification strategy | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861271 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Merch
177 | Comm | SNO | MLL/MIL |  |  | Pre-Seed Program Support - any trial sizes or plans? | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Merch
178 | Comm | SNO | MLL/MIL |  |  | Confirm if we need Sachets for Sales Samples | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Merch
180 | Comm | SNO | MLL/MIL |  |  | Is Direct Store Delivery requested? (applicable on large stream 1s) | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861913 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Conversion Strat
181 | Comm | SNO | MLL/MIL |  |  | Confirm if other elements of Bundle will be managed via Forecast / Order Compliance | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Conversion Strat
182 | Comm | SNO | MLL/MIL |  |  | Any Changes/Needs for Flex Truck Allowance & Other Speed to Shelf Programs | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Conversion Strat
183 | Comm | SNO | MLL/MIL |  |  | Clarify any specific First Delivery Date Customer Expectations | 6d | Tue 9/22/26 | Tue 9/29/26 | 168172 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Conversion Strat
184 | Comm | SNO | MLL/MIL |  |  | Complete any Flow Behind vs. Pipeline Capabilities Specifics | 6d | Tue 9/22/26 | Tue 9/29/26 | 168172 | 861 | Commercial Concept/Sell-In | Design |  | All | Mandatory |  | MR: Cust Sellin: Conversion Strat
185 | Comm | SNO | MLL/MIL |  |  | Confirm if any Mixed impact of Planogram (POG) resets across top retailers vs dates | 6d | Tue 9/22/26 | Tue 9/29/26 | 168 | 861 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Cust Sellin: Conversion Strat
186 | Comm | Sales | Sales | A |  | Lock overall selling framework (incl. category growth, profitability, differentiation, External Relations story etc.) | 1w | Fri 10/2/26 | Thu 10/8/26 | 401170208 | 673,188,5 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula | Ready to Invest/Commit | MR: Customer Selling
187 | Comm | A&I | A&I | A |  | Volume forecast agreed by Region | 1w | Thu 3/2/28 | Thu 3/9/28 | 513170 | 650 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Market Readiness
188 | Comm | Sales/Finance | Sales/Finance | A |  | Pricing guidelines locked | 2w | Fri 10/9/26 | Thu 10/22/26 | 401174186 | 513,653,5 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula | Ready to Invest/Commit | Market Readiness
190 | Comm | SNO | IOL | A |  | Define the Rundown plan | 1w | Tue 3/14/28 | Mon 3/20/28 | 163SS,168,172 | 191 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Inventory
191 | Comm | SNO | IOL | A |  | Inventory mgmt plan | 1mo | Tue 3/21/28 | Wed 4/19/28 | 190168 | 192 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Inventory
192 | Tech | SNO | SNO | A |  | Develop transition plans and associated costs | 1w | Thu 4/20/28 | Wed 4/26/28 | 191 | 662 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | MR: Inventory
193 | Comm | Sales | Sales | A |  | Update Customer Value Assessment (CVA) | 2w | Mon 2/16/26 | Fri 2/27/26 | 88 | 583582 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Market Readiness
196 | Comm | Mktg | Mktg |  |  | Brief Creative team | 2.5w | Mon 4/20/26 | Wed 5/6/26 | 97 | 197203 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
197 | Comm | Mktg | Mktg |  |  | 1 st Client presentation (Top 1-3 Key Ideas) | 2.5w | Wed 5/6/26 | Fri 5/22/26 | 196 | 198 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
198 | Comm | Mktg | Eng |  |  | Creative/Communication Brief re-approved | 3w | Mon 5/25/26 | Fri 6/12/26 | 197 | 199 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
199 | Comm | Mktg | Eng |  |  | REDO - 1 st Client presentation (Top 1-3 Key Ideas) with GM | 2w | Mon 6/15/26 | Fri 6/26/26 | 198 | 201,204,200SS+1w | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
200 | Comm | A&I | A&I |  |  | Lead Testing (prep-4 and testing) | 1d | Mon 6/22/26 | Mon 6/22/26 | 199SS+1w | 201 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
201 | Comm | Mktg | Eng | A |  | Boards Approved - Lock MNI (incl revisions) | 2d | Mon 6/29/26 | Tue 6/30/26 | 199200 | 204,202,121,205,5 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory | Ready to Invest/Commit | CR: Comm strategy
202 | Comm | Mktg | Eng |  |  | Hand off MNI to IAT | 1d | Wed 7/1/26 | Wed 7/1/26 | 201 | 277 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
203 | Comm | Mktg | Mktg |  |  | Call for Work Development - start CPC | 4w | Wed 5/6/26 | Wed 6/3/26 | 196 | 215283 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
204 | Comm | Mktg | Eng |  |  | Kick-off Agency work on Elements to Pre-Table Top | 0d | Tue 6/30/26 | Tue 6/30/26 | 199201 | 279280281282278 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: Comm strategy
205 | Comm | Mktg | Mktg |  |  | Marketing Toolbox elements ID'ed | 1w | Wed 7/1/26 | Tue 7/7/26 | 201 | 207 | Commercial Concept/Sell-in | Discover |  | Commercial Facing | Mandatory |  | Commercial Readiness
206 | Comm | Sales | Sales |  |  | Shopper Market strategy locked | 2w | Tue 2/24/26 | Mon 3/9/26 | 167 | 66683 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Package, Artwork, Formula |  | Commerical Readiness
207 | Comm | Mktg | Mktg |  |  | Initiative toolbox elements complete | 2mo | Wed 7/8/26 | Mon 9/7/26 | 205 | 695 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Commerical Readiness
208 | Comm | A&I | A&I |  | LP | Trial Potential Assessment (TPA) completed | 1d | Thu 10/1/26 | Thu 10/1/26 | 271,89 | 583687186 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | Commerical Readiness
211 | Comm | Mktg | Mktg |  |  | Claims Demo Brief Updated - R1 | 5w | Mon 3/30/26 | Fri 5/1/26 | 90,77 | 271212 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Dev
212 | Comm | Mktg | Mktg |  |  | Assess the Claims Landscape | 1w | Mon 8/16/27 | Fri 8/20/27 | 567FS+2w,211 | 213 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Dev
213 | Comm | Mktg | Mktg |  |  | Prepare Claims Screener List | 1w | Mon 8/23/27 | Fri 8/27/27 | 212 | 214 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Dev
214 | Comm | Mktg | Mktg |  |  | Approve with Legal and PR | 1w | Mon 8/30/27 | Fri 9/3/27 | 213 | 217215 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Dev
215 | Comm | Mktg | Mktg |  |  | Claims Demo Brief Updated - R2 | 2d | Mon 9/6/27 | Tue 9/7/27 | 203214 | 272273 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Dev
217 | Comm | A&I | A&I | A | LP | Approve Claims for Submission | 1w | Mon 9/6/27 | Fri 9/10/27 | 214 | 218 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
218 | Comm | A&I | A&I |  | LP | Field Claims | 3w | Mon 9/13/27 | Fri 10/1/27 | 217 | 219 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
219 | Comm | A&I | A&I |  | LP | Claims Qualification Results Available | 3d | Mon 10/4/27 | Wed 10/6/27 | 218 | 220 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
220 | Comm | A&I | A&I | A | LP | Claims Approved for Use | 17d | Thu 10/7/27 | Fri 10/29/27 | 219 | 699 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
222 | Comm | A&I | A&I |  | LP | Define Consumer Study CRP | 1w | Mon 7/26/27 | Fri 7/30/27 | 567FS-1w | 223SS,227SS,228SS | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
223 | Comm | A&I | A&I |  | LP | Determine legs for Claims S | 1w | Mon 7/26/27 | Fri 7/30/27 | 222SS | 224 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
224 | Comm | A&I | A&I | A | LP | CS CRP Approved | 0d | Fri 7/30/27 | Fri 7/30/27 | 223 | 225FF,237,247 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
225 | Tech | PD | PR | A | LP | Success Criteria Per Leg Locked for CS | 49w | Fri 7/31/26 | Fri 7/30/27 | 224FF | 227 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
226 | Tech | PD | PD | A | LP | Product Prep for CS | 38d | Mon 8/2/27 | Wed 9/22/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
227 | Tech | Process | Process |  | LP | Identify RM's needed for wide range of locked formulas | 1d | Mon 8/2/27 | Mon 8/2/27 | 222SS,225 | 228 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
228 | Tech | Process | Process |  | LP | Order RM's for CS | 12d | Tue 8/3/27 | Wed 8/18/27 | 227,222SS | 229 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
229 | Tech | Process | Process |  | LP | RM's Matls Received \ for CS | 1d | Thu 8/19/27 | Thu 8/19/27 | 228 | 231 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
230 | Tech | Process | Process | A | LP | CS Product Prep | 24d | Fri 8/20/27 | Wed 9/22/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
231 | Tech | Process | Process |  | LP | Preview batch making for CS | 2d | Fri 8/20/27 | Mon 8/23/27 | 229 | 232,233SS | New Claims | Design |  | Commercial Facing | LP: Claims Screener
232 | Tech | PR | PR |  | LP | Preview batch stability for CS | 2w | Tue 8/24/27 | Mon 9/6/27 | 231 | 234240 | New Claims | Design |  | Commercial Facing | LP: Claims Screener
233 | Tech | Process | Process |  | LP | Renew CS MFC's (Sport) | 2w | Fri 8/20/27 | Thu 9/2/27 | 231SS | 243 | New Claims | Design |  | Commercial Facing | LP: Claims Screener
234 | Tech | Process | Process |  | LP | Final product making for CS | 2d | Tue 9/7/27 | Wed 9/8/27 | 232 | 235 | New Claims | Design |  | Commercial Facing | LP: Claims Screener
235 | Tech | PR | PR | A | LP | Final product testing for CS (approval, documents, etc) | 14ed | Wed 9/8/27 | Wed 9/22/27 | 234 | 240252 | New Claims | Design |  | Commercial Facing | LP: Claims Screener
236 | Tech | PR | Process |  | LP | Packout Prep for CS | 51d | Mon 8/2/27 | Mon 10/11/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
237 | Tech | PR | PR |  |  | Order Packing Materials | 1w | Mon 8/2/27 | Fri 8/6/27 | 224 | 238 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
238 | Tech | PR | Process |  | LP | Receive CS Packing Materials | 36d | Mon 8/9/27 | Mon 9/27/27 | 237 | 240 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
239 | Tech | PR | Process |  | LP | CS Packing | 8d | Tue 9/28/27 | Thu 10/7/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
240 | Tech | PD | PR |  | LP | Pack-out CS Product for CS | 1d | Tue 9/28/27 | Tue 9/28/27 | 232235238 | 241245 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
241 | Tech | PD | PR |  | LP | Micro CS Product for CS | 7d | Wed 9/29/27 | Thu 10/7/27 | 240 | 244 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
242 | Tech | PR | PR |  | LP | CS Test Materials/ Clearance | 26d | Fri 9/3/27 | Fri 10/8/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
243 | Tech | PR | PR |  | LP | Submit SMART | 4w | Fri 9/3/27 | Thu 9/30/27 | 233 | 244 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
244 | Tech | PR | PR | A | LP | Complete SMART | 1d | Fri 10/8/27 | Fri 10/8/27 | 241254243 | 245 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
245 | Tech | PD | PR | A | LP | Product shipped for CS | 1d | Mon 10/11/27 | Mon 10/11/27 | 240244 | 256 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
246 | Comm | Mktg | Mktg | A | LP | Concept Delivery for CS | 44d | Mon 8/2/27 | Thu 9/30/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
247 | Comm | A&I | A&I |  | LP | Conduct Client Objectives Meeting - Round 1 | 2d | Mon 8/2/27 | Tue 8/3/27 | 224 | 250,248FS+2w | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
248 | Comm | A&I | A&I |  | LP | Conduct Client Objectives Meeting - Round 2 | 1d | Wed 8/18/27 | Wed 8/18/27 | 247FS+2w | 251FS+1w,252FS+1w | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
249 | Comm | Mktg | Mktg |  | LP | CS Concept | 42d | Wed 8/4/27 | Thu 9/30/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
250 | Comm | A&I | A&I |  | LP | Draft After Use Questionnaire Delivered (3/30) | 7d | Wed 8/4/27 | Thu 8/12/27 | 247 | 253 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
251 | Comm | A&I | A&I |  | LP | Questions Finalized for Pre-Screening OQ Groups | 6d | Thu 8/26/27 | Thu 9/2/27 | 248FS+1w | 252 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
252 | Comm | A&I | A&I |  | LP | Pre- Screening OQ Groups | 6d | Thu 9/23/27 | Thu 9/30/27 | 235,248FS+1w,251 | 257 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
253 | Comm | Mktg | Mktg | A | LP | Final AU CS Questionnaire Input - Team | 1w | Fri 8/13/27 | Thu 8/19/27 | 250 | 254 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
254 | Comm | A&I | A&I |  | LP | Provide AU CS Questionnaire Feedback | 2d | Fri 8/20/27 | Mon 8/23/27 | 253 | 244259257 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
255 | Comm | A&I | A&I |  | LP | CS Execution | 21d | Tue 10/12/27 | Tue 11/9/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
256 | Comm | A&I | A&I |  | LP | CS Product Organized for Placement | 1d | Tue 10/12/27 | Tue 10/12/27 | 245 | 257 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
257 | Comm | A&I | A&I |  | LP | CS Start Date/Field Concept | 0d | Tue 10/12/27 | Tue 10/12/27 | 252256254 | 258 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
258 | Comm | A&I | A&I |  | LP | CS Usage | 2w | Wed 10/13/27 | Tue 10/26/27 | 257 | 259SS+1d | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
259 | Comm | A&I | A&I |  | LP | Afteruse Field Start Date | 10d | Thu 10/14/27 | Wed 10/27/27 | 258SS+1d,254 | 260 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
260 | Comm | A&I | A&I |  | LP | T2/3 Box Respondents Identified | 1w | Thu 10/28/27 | Wed 11/3/27 | 259 | 265261 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
261 | Comm | A&I | A&I |  | LP | Scheduling of Respondents | 4d | Thu 11/4/27 | Tue 11/9/27 | 260 | 263 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
262 | Comm | A&I | A&I | A | LP | CS Results | 17d | Thu 11/4/27 | Fri 11/26/27 |  |  | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
263 | Comm | A&I | A&I |  | LP | CS At Home Interviews (Qualitative) | 1w | Wed 11/10/27 | Tue 11/16/27 | 261 | 264 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
264 | Comm | A&I | A&I |  | LP | CS Group Interviews | 1w | Wed 11/17/27 | Tue 11/23/27 | 263 | 266 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
265 | Comm | A&I | A&I |  | LP | CS Quantitative Results | 2w | Thu 11/4/27 | Wed 11/17/27 | 260 | 266 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
266 | Comm | A&I | A&I |  | LP | CS Top Claims Available for Item X | 3d | Wed 11/24/27 | Fri 11/26/27 | 265264 | 268 | New Claims | Design |  | Commercial Facing | LP: Claims Strengthening Test |  | CR: PTT: Claims LP
267 | Comm | A&I | A&I |  | LP | Claims Qualification (FMOT) R2 | 20d | Mon 11/29/27 | Fri 12/24/27 |  |  | New Claims | Design |  | Commercial Facing |  |  | CR: PTT: Claims Qual
268 | Comm | A&I | A&I |  | LP | Approve Claims for Submission | 2d | Mon 11/29/27 | Tue 11/30/27 | 266 | 269 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
269 | Comm | A&I | A&I |  | LP | Field Claims | 3w | Wed 12/1/27 | Tue 12/21/27 | 268 | 270 | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
270 | Comm | A&I | A&I |  | LP | Claims Qualification Results Available | 3d | Wed 12/22/27 | Fri 12/24/27 | 269 |  | New Claims | Design |  | Commercial Facing | LP: Claims Screener |  | CR: PTT: Claims Qual
271 | Comm | Mktg | Mktg |  |  | Define FMOT guidelines for Claims | 1d | Wed 9/30/26 | Wed 9/30/26 | 211176170 | 208272 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Qual
272 | Comm | Mktg | Eng |  |  | Claims summary updated - R3 | 2d | Wed 9/8/27 | Thu 9/9/27 | 215271 | 273 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Qual
273 | Comm | Mktg | Eng |  |  | Claims Summary Updated - R4 (incl agency needs) | 1w | Fri 9/10/27 | Thu 9/16/27 | 215272283 | 274 | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Qual
274 | Comm | Mktg | Eng |  |  | Claims Summary Locked (All) | 8d | Fri 9/17/27 | Tue 9/28/27 | 284273 |  | New Claims | Design |  | Commercial Facing | Claims |  | CR: PTT: Claims Qual
276 | Comm | Mktg | Eng |  |  | TV Plans | 49d | Thu 7/2/26 | Tue 9/8/26 |  | 283 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
277 | Comm | Mktg | Eng |  |  | Agency to refine boards for Digimatics | 1w | Thu 7/2/26 | Wed 7/8/26 | 202 | 278 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
278 | Comm | Mktg | Eng |  |  | Lock on Bds for Digimatics | 2mo | Thu 7/9/26 | Tue 9/8/26 | 277204 | 706715718 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
279 | Comm | Mktg | Eng |  |  | Print Plans | 5w | Wed 7/1/26 | Tue 8/4/26 | 204 | 283724 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
280 | Comm | Mktg | Eng |  |  | Digital Plans | 5w | Wed 7/1/26 | Tue 8/4/26 | 204 | 283726 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
281 | Comm | Mktg | Eng |  |  | In Store Plans | 5w | Wed 7/1/26 | Tue 8/4/26 | 204 | 283731 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
282 | Comm | Mktg | Eng |  |  | Media Plans | 5w | Wed 7/1/26 | Tue 8/4/26 | 204 | 283734 | Commercial Concept/Sell-In, New Claims | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
283 | Comm | Mktg | Eng |  |  | Review of Pre TableTop Documents | 2d | Wed 9/9/26 | Thu 9/10/26 | 2.7628e+21 | 284273 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
284 | Comm | Mktg | Eng | A |  | Approve Pre TableTop | 1mo | Fri 9/11/26 | Mon 10/12/26 | 283 | 685,724,734,731,726FS-4w,706FS-2w,6,274 | Commercial Concept/Sell-In | Design |  | Commercial Facing | Mandatory |  | CR: PTT: Mktg Elements
287 | Comm | Design | Design |  |  | 2D Package Qualifications | 1w | Thu 8/6/26 | Wed 8/12/26 | 152157106 | 288307 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
288 | Comm | Design | Design |  |  | FMOT Claim & Qualifications | 1w | Thu 8/13/26 | Wed 8/19/26 | 287 | 289307 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
289 | Comm | Design | Design | A |  | Lead package commercially qualified | 1w | Thu 8/20/26 | Thu 8/27/26 | 288 | 290 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
290 | Comm | Design | Design |  |  | Pkg design meets MSR | 1w | Fri 8/28/26 | Thu 9/3/26 | 289 | 291 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
291 | Comm | Design | Design | A |  | Design review with Design Manager | 1d | Fri 9/4/26 | Fri 9/4/26 | 290 | 292 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
292 | Comm | Design | Design |  |  | 1st Design Refinements | 5d | Mon 9/7/26 | Fri 9/11/26 | 291 | 294293 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
293 | Comm | Design | Design | A |  | Round 1 - Review mtg w/ "C"' | 1d | Mon 9/14/26 | Mon 9/14/26 | 292 | 294 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
294 | Comm | Design | Design | A |  | Prelim. Legal Review with Legal- Name and Designs | 1d | Tue 9/15/26 | Tue 9/15/26 | 292293 | 297295 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
295 | Comm | Design | Design |  |  | 2nd Design Refinements | 3d | Wed 9/16/26 | Fri 9/18/26 | 294 | 296 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
296 | Comm | Design | Design |  |  | Create stimulus for research | 2w | Mon 9/21/26 | Fri 10/2/26 | 295 | 298 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
297 | Comm | Design | Design | A |  | Package & Naming Approval | 1d | Wed 9/16/26 | Wed 9/16/26 | 294 | 298 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
298 | Comm | A&I | A&I |  |  | Qualitative Research | 5d | Mon 10/5/26 | Fri 10/9/26 | 296297 | 299320 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
299 | Comm | A&I | A&I |  |  | Meeting w/ "A" Research findings | 1d | Mon 10/12/26 | Mon 10/12/26 | 298 | 300 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
300 | Comm | A&I | A&I |  |  | Research Learnings & Refinements | 12d | Tue 10/13/26 | Thu 10/29/26 | 299 | 301302 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
301 | Comm | Design | Design |  |  | Pkg design meets MSR | 1w | Fri 10/30/26 | Thu 11/5/26 | 300 | 302 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
302 | Comm | Design | Design | A |  | Prelim. Legal Review with Legal- Name and Designs | 1d | Fri 11/6/26 | Fri 11/6/26 | 300301 | 303307 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
303 | Comm | Design | Design | A |  | Approve Shelf Views/Quals Stimulus (ex. Item color, labels/naming/caps) | 1d | Mon 11/9/26 | Mon 11/9/26 | 302 | 304 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
304 | Comm | Design | Agency |  |  | Continued Revisions on Design | 6d | Tue 11/10/26 | Tue 11/17/26 | 303 | 314 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
307 | Comm | IDM | IL |  | LP | Determine Images needed for Shelf View (get VL shelf) | 1d | Mon 11/9/26 | Mon 11/9/26 | 302287288 | 308 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
308 | Comm | Design | Agency |  | LP | Deliver Images to Agency for Shelf Views | 2d | Tue 11/10/26 | Wed 11/11/26 | 307 | 309 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
309 | Comm | Design | Agency |  | LP | Update VL shelves with other brand Images | 2d | Thu 11/12/26 | Fri 11/13/26 | 308 | 310 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
310 | Comm | A&I/Design | A&I/Design | A | LP | Determine Stimulus with A&I/Design | 0d | Fri 11/13/26 | Fri 11/13/26 | 309 | 311 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
311 | Comm | Design | Design | A | LP | Develop Stimulus with A&I/Design | 2d | Mon 11/16/26 | Tue 11/17/26 | 310 | 312 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
312 | Comm | A&I | A&I |  | LP | Conduct 1st Quals | 2d | Wed 11/18/26 | Thu 11/19/26 | 311 | 313 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
313 | Comm | A&I | A&I |  | LP | Summarize 1st Qual Results | 0d | Thu 11/19/26 | Thu 11/19/26 | 312 | 314 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | AW: Shelf Quals
314 | Comm | Design | Agency |  |  | Continued Revisions on Design | 6d | Fri 11/20/26 | Fri 11/27/26 | 313304 | 315,316SS | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
315 | Comm | Design | Design |  |  | Final Round of Progress since Quals | 2d | Mon 11/30/26 | Tue 12/1/26 | 314 | 317 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
316 | Comm | Design | Design | A | LP | Prelim. Legal Review with Legal- Name and Designs | 1w | Fri 11/20/26 | Thu 11/26/26 | 314SS | 317 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
317 | Comm | IDM | IL | A |  | GM Approve Pkg Revisions (colors, artwork, etc) | 0d | Tue 12/1/26 | Tue 12/1/26 | 315316 | 328336 | New Package, New Brand Architecture | Design |  | Commercial Facing | Package, Brand Architecture |  | AW: Design/Explore
320 | Comm | IDM/A&I | A&I/IL |  | LP | Kickoff 2D Work (A&I mtg-2, Agency Mtg-1) | 6d | Mon 10/12/26 | Mon 10/19/26 | 298 | 321322 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
321 | Comm | A&I | A&I | A | LP | Approve 2D Scope and PACE | 1d | Tue 10/20/26 | Tue 10/20/26 | 320 | 324 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
322 | Comm | Sales | Sales |  | LP | Develop the Shelf POG’s for 2D | 1.5d | Tue 10/20/26 | Wed 10/21/26 | 320 | 323 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
323 | Comm | Sales | Sales/Nate |  | LP | Decision for Footprints/Sizes for 2D BISI-P | 1.5d | Wed 10/21/26 | Thu 10/22/26 | 322 | 324 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
324 | Comm | IDM/Sales | IL/Sales | A | LP | Lock Shelf POG’s and label spots/develop SKU list/number coding | 0d | Thu 10/22/26 | Thu 10/22/26 | 323321 | 325326 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
325 | Comm | Mktg | Mktg |  | LP | Decision for SKUs for 2D BISI-P – complete SKU list/number coding document | 6d | Fri 10/23/26 | Fri 10/30/26 | 324 | 328 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
326 | Comm | A&I/Sales | A&I/Sales |  | LP | Send DRAFT shelf to PRS and receive questionnaire from PRS | 3d | Fri 10/23/26 | Tue 10/27/26 | 324 | 327 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
327 | Comm | A&I | A&I |  | LP | Revise Questionnaire if needed | 6d | Wed 10/28/26 | Wed 11/4/26 | 326 | 332 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
328 | Comm | Design | Agency |  | LP | Time when Final Images for 2D BISI-P (barring GM approval of overall shelf) | 7d | Wed 12/2/26 | Thu 12/10/26 | 317325 | 329 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
329 | Comm | A&I | A&I | A | LP | Send final 2D BISI-P shelf to P&G for GM review on 24th | 1d | Fri 12/11/26 | Fri 12/11/26 | 328 | 331 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
330 | Comm | Design | Design/Agency |  | LP | Send any last minute changes on 2D BISI-P Images to PRS by noon EST | 1d | Mon 12/28/26 | Mon 12/28/26 | 331 | 332 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
331 | Comm | A&I/Design | A&I/Design | A | LP | Approval of 2D BISI-P Submissions (chose between options if necessary) | 2w | Mon 12/14/26 | Fri 12/25/26 | 329 | 330,348,367,368SS | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
332 | Comm | A&I | PRS |  | LP | Prepare stimulus for 2D BISI-P | 6d | Tue 12/29/26 | Tue 1/5/27 | 330327 | 333 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
333 | Comm | A&I | A&I |  | LP | Conduct 2D BISI-P | 25d | Wed 1/6/27 | Fri 2/12/27 | 332 | 334 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
334 | Comm | A&I | A&I | A | LP | Results, Design Team Approval – Top Line Planned Changes Approved | 2w | Mon 2/15/27 | Fri 3/12/27 | 333 | 358 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 2D BISIP |  | LP: 2D BISIP
336 | Comm | A&I | A&I |  | LP | Kick off 3D Shelf Test Work | 6d | Wed 12/2/26 | Wed 12/9/26 | 317 | 337338 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
337 | Comm | IDM/A&I | A&I/IL | A | LP | Approve Scope and PACE | 1d | Thu 12/10/26 | Thu 12/10/26 | 336 | 352341343 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
338 | Comm | Sales | Sales |  | LP | Develop the Shelf POG’s 3D | 1.5d | Thu 12/10/26 | Fri 12/11/26 | 336 | 339 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
339 | Comm | Sales | Sales/Nate |  | LP | Decision for Footprints/Sizes for 3D Shelf Test | 1.5d | Fri 12/11/26 | Mon 12/14/26 | 338 | 340 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
340 | Comm | IDM/Sales | IL/Sales | A | LP | Lock Control Shelf POG’s and label spots/develop SKU list/number coding | 0d | Mon 12/14/26 | Mon 12/14/26 | 339 | 342 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
341 | Comm | Sales | Sales/Sales | A | LP | Lock New Modular POG's | 1w | Fri 12/11/26 | Thu 12/17/26 | 337 | 342360359 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
342 | Comm | Mktg | Mktg |  | LP | Decision for SKUs for 3D Shelf Test – complete SKU list/number coding document | 3d | Fri 12/18/26 | Tue 12/22/26 | 340341 | 345 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
343 | Comm | A&I | Sales |  | LP | Draft Shelf Test | 2w | Fri 12/11/26 | Thu 12/24/26 | 337 | 352 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
344 | Comm | A&I | A&I |  | LP | Get Product for 3D Shelf Test | 18d | Tue 12/22/26 | Fri 1/15/27 |  |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
345 | Comm | A&I | A&I |  | LP | Send list of materials (e.g. cartons/bottle/labels/caps) needed to PS reps | 0d | Tue 12/22/26 | Tue 12/22/26 | 342 | 346347349 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
346 | Comm | MPD | MPD |  | LP | Obtain 'fake materials if needed' - mock up/sprayed/etc | 3w | Wed 12/23/26 | Wed 1/13/27 | 345 | 350 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
347 | Comm | MPD | MPD |  | LP | Obtain Primary Pack (e.g., Base Bottles/Cartons/etc) | 2w | Wed 12/23/26 | Wed 1/6/27 | 345 | 350 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
348 | Comm | Design | Design |  | LP | Generate Labels for Primary Pack (e.g., caps, cartons, bottle) | 2d | Mon 12/28/26 | Tue 12/29/26 | 331,77 | 350 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
349 | Comm | Design | MPD |  | LP | Order/Obtain any additional materials needed | 2w | Wed 12/23/26 | Wed 1/6/27 | 345 | 350 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
350 | Comm | Design | Design |  | LP | Assemble Primary Packs for Shelf Test | 2d | Thu 1/14/27 | Fri 1/15/27 | 349346347348 | 351 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
351 | Comm | Design | Design |  | LP | Items due to BRIC for Shelf Build | 0d | Fri 1/15/27 | Fri 1/15/27 | 350 | 354 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
352 | Comm | A&I | A&I |  | LP | Revise Shelf Test if needed | 2d | Fri 12/25/26 | Mon 12/28/26 | 337343 | 353 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
353 | Comm | A&I | A&I | A | LP | Approval of 3D Shelf Test | 2d | Tue 12/29/26 | Wed 12/30/26 | 352 | 354 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
354 | Comm | A&I | A&I/A&I |  | LP | Conduct Test BRIC Shelf Test/Quals | 14d | Mon 1/18/27 | Thu 2/4/27 | 351353 | 355 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
355 | Comm | A&I | A&I/A&I | A | LP | Results BRIC Shelf Test/Quals | 0d | Thu 2/4/27 | Thu 2/4/27 | 354 | 358356683 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
356 | Comm | Sales | Sales |  | LP | Lead package commercially qualified | 1d | Fri 2/5/27 | Fri 2/5/27 | 355 | 373 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D Shelf Test |  | LP: 3D Shelf Test for 3D BISIP
358 | Comm | Design | Design | A | LP | Research Learnings & Refinements from 2D BISI-P | 2w | Mon 3/15/27 | Fri 4/9/27 | 355334 | 362,370,380FS+12d | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
359 | Comm | Design | Design |  | LP | Order/Receive Additional Materials for 3D BISI-P primary packs | 8w | Fri 12/18/26 | Fri 2/12/27 | 341 | 376 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
360 | Comm | Design | Design |  | LP | Order New Primary Packs for 3D BISI-P | 5w | Fri 12/18/26 | Fri 1/22/27 | 341 | 361 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
361 | Comm | Design | Design |  | LP | Receive Primary Pack for 3D BISI-P | 0d | Thu 10/14/27 | Thu 10/14/27 | 360631 | 375 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
362 | Comm | Design | Design |  | LP | Update control to test POGs for confirmed improvements on eye-tracking | 3ed | Fri 4/9/27 | Mon 4/12/27 | 358 | 363 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
363 | Comm | Design | Design |  | LP | 2D BISI-P Eye Tracking Update | 5d | Tue 4/13/27 | Mon 4/19/27 | 362 | 364 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
364 | Comm | Design | Design |  | LP | Results from Eye Tracking Update | 3d | Tue 4/20/27 | Thu 4/22/27 | 363 | 365,549FS+25d | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
365 | Comm | Design | Design | A | LP | Slight Changes for Labels/Approval | 4d | Fri 4/23/27 | Wed 4/28/27 | 364 | 374373 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
366 | Comm | Design | Design |  | LP | Changes to Claims for 3D BISI-P | 89d | Mon 12/14/26 | Thu 4/15/27 |  |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
367 | Comm | Mktg/PR | Mktg/PR |  | LP | Identify Claims/Benefits for Package Communication | 1w | Mon 12/28/26 | Fri 1/1/27 | 331 |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
368 | Comm | PR | PR |  | LP | Review Claims with Legal | 2w | Mon 12/14/26 | Fri 12/25/26 | 331SS | 369 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
369 | Comm | Design | Design |  | LP | Final minor refinements per feedback | 2d | Mon 12/28/26 | Tue 12/29/26 | 368 |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
370 | Comm | Design | Design |  | LP | Identify Updated Claims/Benefits for additional On Pack communication | 0d | Fri 4/9/27 | Fri 4/9/27 | 358,91 | 371 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
371 | Comm | PR | PR |  | LP | Review Claims with Legal | 4d | Mon 4/12/27 | Thu 4/15/27 | 370 | 372 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
372 | Comm | Design | Design |  | LP | Final minor refinements per feedback | 0d | Thu 4/15/27 | Thu 4/15/27 | 371 | 373376 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
373 | Comm | Design | Design | A | LP | Lock Package for 3D BISIP | 3d | Wed 11/17/27 | Fri 11/19/27 | 356607372365 | 374 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
374 | Comm | Design | Design |  | LP | Order 3D BISI-P Labels from Haney | 0d | Fri 11/19/27 | Fri 11/19/27 | 365373 | 375 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
375 | Comm | Design | Design |  | LP | Place Labels on Primary Packs for 3D BISI-P | 2w | Mon 11/22/27 | Fri 12/3/27 | 374361 | 378,377SS | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
376 | Comm | Design | Design |  | LP | Order any Stickers and put on materials | 2w | Fri 4/16/27 | Thu 4/29/27 | 372359 | 377 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
377 | Comm | Design | Design |  | LP | Place Stickers/Etc on Primary Packs | 0d | Mon 11/22/27 | Mon 11/22/27 | 375SS,376 | 378 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
378 | Comm | Design | Design |  | LP | Primary Pack Due for 3D BISI-P | 7d | Mon 12/6/27 | Tue 12/14/27 | 375377 | 383 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
380 | Comm | A&I | A&I |  | LP | 3D BISI-P CRP Approved/PO Approved/Final POG confirmed | 5d | Wed 4/28/27 | Tue 5/4/27 | 358FS+12d | 386,381SS,383 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
381 | [5 empty] | 3D BISI-P On-boarding Meeting | 5d | Wed 4/28/27 | Tue 5/4/27 | 380SS | 382 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
382 | Comm | A&I | A&I |  | LP | Draft 3D BISI-P Questionnaire to P&G | 4d | Wed 5/5/27 | Mon 5/10/27 | 381 | 384 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
383 | Comm | A&I | A&I |  | LP | PRS Receives Finished 3D BISI-P Bottles | 0d | Tue 12/14/27 | Tue 12/14/27 | 378380 | 386 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
384 | Comm | A&I | A&I |  | LP | 3D BISI-P Questionnaire Feedback from P&G | 5d | Tue 5/11/27 | Mon 5/17/27 | 382 | 385 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
385 | Comm | A&I | A&I | A | LP | Final 3D BISI-P Questionnaire Approval | 3d | Tue 5/18/27 | Thu 5/20/27 | 384 |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
386 | Comm | A&I | A&I |  | LP | Shopping/Photography/2D Visual Graphics complete | 5d | Wed 12/15/27 | Tue 12/21/27 | 380383 | 387 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
387 | Comm | A&I | A&I | A | LP | P&G Approval of Final 3D BISI-P Stimuli | 2d | Wed 12/22/27 | Thu 12/23/27 | 386 | 388 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
388 | Comm | A&I | A&I |  | LP | Prep for Fielding of 3D BISI-P | 5d | Fri 12/24/27 | Thu 12/30/27 | 387 | 389 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
389 | Comm | Design | Design |  | LP | Conduct 3D BISI-P | 9d | Fri 12/31/27 | Wed 1/12/28 | 388 | 390 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
390 | Comm | A&I | A&I |  | LP | 3D BISI-P Results | 2w | Thu 1/13/28 | Wed 1/26/28 | 389 | 391 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
391 | Comm | A&I | A&I |  | LP | Minor Refinements from 3D BISI-P | 1w | Thu 1/27/28 | Wed 2/2/28 | 390 | 392 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
392 | Comm | A&I | A&I | A | LP | Approval for Package | 1w | Thu 2/3/28 | Wed 2/9/28 | 391 | 668 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: 3D BISIP |  | LP: 3D BISIP
394 | Comm | Design | Design |  | LP | Provide Packaging Design | 2w | Mon 7/20/26 | Fri 7/31/26 | 156 | 395SS | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
395 | Comm | Mktg | Mktg |  | LP | Naming | 2w | Mon 7/20/26 | Fri 7/31/26 | 394SS |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
396 | Comm | Mktg | Mktg |  | LP | Provide Concept | 2w | Mon 5/11/26 | Fri 5/22/26 | 86,87 | 397 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
397 | Comm | GM LT | Finance | A | LP | Approve VL Input | 1d | Mon 5/25/26 | Mon 5/25/26 | 396 | 398399 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
398 | Comm | A&I | A&I |  | LP | Concept Evaluator | 8w | Tue 5/26/26 | Wed 7/22/26 | 397 | 401402404 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
399 | Comm | A&I | A&I |  | LP | VL Test | 12w | Tue 5/26/26 | Wed 8/19/26 | 397 | 401402 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
400 | Comm | A&I | A&I |  | LP | VL Results Available | 45d | Thu 7/23/26 | Wed 9/23/26 |  |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
401 | Comm | A&I | A&I |  | LP | Pricing from VL | 2w | Thu 8/20/26 | Wed 9/2/26 | 398399 | 166188405174186 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
402 | Comm | A&I | A&I |  | LP | Volume from VL | 2w | Thu 8/20/26 | Wed 9/2/26 | 398399 | 405 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
403 | Comm | A&I | A&I | A | LP | VL Results Approved | 45d | Thu 7/23/26 | Wed 9/23/26 |  |  | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
404 | Comm | A&I | A&I | A | LP | Results Compiled and initial Concept Results Shared | 1w | Thu 7/23/26 | Wed 7/29/26 | 398 | 405 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
405 | Comm | Mktg | Mktg | A | LP | Concept, Pricing, Appeal Results Approved | 3w | Thu 9/3/26 | Wed 9/23/26 | 401402404 | 647,168FS-2w,612SF+6d,668 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: Virtual Launch |  | LP: Virtual Launch
407 | Tech | PR | PR | A | LP | Define Consumer Usage Check (CUC) CRP | 2d | Tue 7/28/26 | Thu 7/30/26 | 589 | 408410429 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
408 | Tech | PR | PR | A | LP | Success Criteria Per Leg Locked | 1d | Fri 7/31/26 | Fri 7/31/26 | 407 | 410 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
409 | Tech | PD | PD |  | LP | Product Prep for CUC | 100d | Mon 8/3/26 | Sat 12/19/26 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
410 | Tech | PD | PD |  | LP | Formulas defined and preliminary testing confirms that success criteria can be met | 20d | Mon 8/3/26 | Fri 8/28/26 | 407408 | 411 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
411 | Tech | Perfume | Perfume |  | LP | CUC Order Materials (perfumes, cartons, etc) | 0d | Fri 8/28/26 | Fri 8/28/26 | 410 | 412 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
412 | Tech | Perfume | Perfume |  | LP | CUC Materials Received | 1d | Mon 8/31/26 | Mon 8/31/26 | 411 | 415413 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
413 | Tech | Perfume | Perfume |  | LP | CUC Materials Leveling/Testing/Stability (perfumes, scents, etc) | 2w | Tue 9/1/26 | Tue 9/15/26 | 412 | 415 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
414 | Tech | PD | PD |  | LP | Round 1 | 43d | Wed 9/16/26 | Fri 11/13/26 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
415 |  | Process | Process |  | LP | CUC Lab batch making (no preview batches) | 5d | Wed 9/16/26 | Tue 9/22/26 | 412413 | 416 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
416 |  | Process | Process |  | LP | CUC Lab batch testing Include Stability Testing (no preview batches) | 3w | Wed 9/23/26 | Tue 10/13/26 | 415 | 417 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
417 |  | Process | Process |  | LP | CUC Final product making | 5d | Wed 10/14/26 | Tue 10/20/26 | 416 | 418 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
418 |  | Process | Process | A | LP | CUC Final product testing (approval, batch records, physical properties) | 3d | Wed 10/21/26 | Fri 10/23/26 | 417 | 420419 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
419 |  |  |  | A | LP | Approval from TST for ordering RM's ahead of final locked formulas to help with time | 3d | Mon 10/26/26 | Wed 10/28/26 | 418 | 459 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
420 |  | Process | Process |  | LP | Root Cause Analysis | 13d | Mon 10/26/26 | Thu 11/12/26 | 418 | 421 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
421 |  |  |  |  | LP | Lock CUC Formulas | 1d | Fri 11/13/26 | Fri 11/13/26 | 420 | 423457522458 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
422 | Tech | PD | PD |  | LP | Round 2 | 25d | Mon 11/16/26 | Sat 12/19/26 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
423 | Tech | Process | Process |  | LP | CUC Preview batch making | 3d | Mon 11/16/26 | Wed 11/18/26 | 421 | 425,424SS | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
424 | Tech | Process | Process |  | LP | Create MFCs | 2w | Mon 11/16/26 | Fri 11/27/26 | 423SS | 434 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
425 | Tech | Process | Process |  | LP | CUC Preview batch testing Include Stability Testing (no preview batches) | 2w | Thu 11/19/26 | Wed 12/2/26 | 423 | 426 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
426 | Tech | Process | Process |  | LP | CUC Final product making | 4d | Thu 12/3/26 | Tue 12/8/26 | 425 | 427 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
427 | Tech | Process | Process | A | LP | CUC Final product testing (approval, batch records, physical properties) | 11ed | Tue 12/8/26 | Sat 12/19/26 | 426 | 435 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
428 | Tech | PR | Process |  | LP | Packout Prep for CUC | 111d | Fri 7/31/26 | Fri 1/1/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
429 | Tech | PR | PR |  | LP | Order Packing Materials | 2d | Fri 7/31/26 | Mon 8/3/26 | 407 | 430 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
430 | Tech | PR | Process |  | LP | Receive Packing Materials | 25d | Tue 8/4/26 | Mon 9/7/26 | 429 | 431 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
431 | Tech | PR | PR |  | LP | CUC Pack-out | 4d | Tue 9/8/26 | Fri 9/11/26 | 430 | 432 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
432 | Tech | PR | PR |  | LP | CUC Micro Test (if applicable) | 5d | Mon 9/14/26 | Fri 9/18/26 | 431 | 435 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
433 | Tech | PR | PR |  | LP | CUC Test Materials/ Clearance | 25d | Mon 11/30/26 | Fri 1/1/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
434 | Tech | PR | PR |  | LP | Submit SMART | 4w | Mon 11/30/26 | Fri 12/25/26 | 424 | 435 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
435 | Tech | PR | PR | A | LP | Complete SMART | 5d | Mon 12/28/26 | Fri 1/1/27 | 432427434 | 436 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
436 | Tech | PR | Process |  | LP | CUC Product Shipped to Test Facility | 3d | Mon 1/4/27 | Wed 1/6/27 | 435 | 437 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
437 | Tech | PR | PR |  | LP | CUC Product Placed | 0d | Wed 1/6/27 | Wed 1/6/27 | 436 | 438 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
438 | Tech | PR | PR |  | LP | CUC Usage | 2w | Thu 1/7/27 | Wed 1/20/27 | 437 | 439SS+1.5w | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
439 | Tech | PR | PR |  | LP | CUC Recall | 5d | Mon 1/18/27 | Mon 1/25/27 | 438SS+1.5w | 440 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
440 | Tech | PR | PR | A | LP | CUC Results Summary | 2d | Mon 1/25/27 | Wed 1/27/27 | 439 | 593478 | New Package, New Formula | Design |  | Technical Scope | LP: Consumer Usage Check |  | LP: CUC
442 | Comm | A&I | A&I |  | LP | Define BASES I CRP | 2w | Tue 8/4/26 | Mon 8/17/26 | 590 | 443 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
443 | Comm | A&I | A&I |  | LP | Determine legs for BASES I | 1w | Tue 8/18/26 | Mon 8/24/26 | 442 | 444 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
444 | Comm | A&I | A&I | A | LP | BASES I CRP Approved | 0d | Mon 8/24/26 | Mon 8/24/26 | 443 | 445FF,459,489FS+3.25mo | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
445 | Tech | PD | PR | A | LP | Success Criteria Per Leg Locked for BASES I | 1w | Tue 8/18/26 | Mon 8/24/26 | 444FF | 447 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
446 | Tech | PD | PD | A | LP | Product Prep for BASES I | 546d | Mon 11/3/25 | Mon 12/6/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
447 | Tech | PD | PD |  | LP | Lock Formulation | 31d | Tue 8/25/26 | Tue 10/6/26 | 445 | 448 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
448 | Tech | PD | PD |  | LP | Stability Testing | 0w | Tue 10/6/26 | Tue 10/6/26 | 447 | 6.006e+17 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
449 | Tech | PD | PD |  | LP | Additional Product Development | 45d | Tue 8/25/26 | Mon 10/26/26 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
450 | Tech | PD | PD |  | LP | Research | 2w | Tue 8/25/26 | Mon 9/7/26 | 518 | 451 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
451 | Tech | PD | PD |  | LP | First Round of Results w New Materials | 29d | Tue 9/8/26 | Fri 10/16/26 | 450 | 453FS-1w,452,455 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
452 | Tech | PD/Process | PD/Process |  | LP | PS&RA Check/Plans to Passport of New Material | 1w | Mon 10/19/26 | Fri 10/23/26 | 451 | 456 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
453 | Tech | PD | PD | A | LP | Stabilty & Performance Testing on First Round | 2w | Mon 10/12/26 | Fri 10/23/26 | 451FS-1w | 456 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
454 | Tech | PD | PD |  | LP | Making of Second Round of Final Package for Testing | 15d | Tue 8/25/26 | Tue 9/15/26 | 518 | 455458 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
455 | Tech | Perfume | Perfume |  | LP | Stability & Performance Testing on Package/Formula | 3d | Mon 10/19/26 | Wed 10/21/26 | 451454 | 461 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
456 | Tech | PD | PD |  | LP | Lock addtl Formula/Package for Testing Legs | 1d | Mon 10/26/26 | Mon 10/26/26 | 452453 | 457 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
457 | Tech | PD | PD | A | LP | BASES I Formulas Locked | 0d | Fri 11/13/26 | Fri 11/13/26 | 421448456 | 597698815458 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
458 | Tech | Process | Process |  | LP | Identify RM's needed for wide range of locked formulas | 1d | Mon 11/16/26 | Mon 11/16/26 | 421454448457 | 459 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
459 | Tech | Process | Process |  | LP | Order RM's/PMs for BASES I | 1d | Fri 10/15/27 | Fri 10/15/27 | 444458419631 | 460 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
460 | Tech | Process | Process |  | LP | RM's/PMs Matls Received \ for BASES I | 1d | Mon 10/18/27 | Mon 10/18/27 | 459 | 464 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
461 | Tech | Process | Process |  | LP | Order Remaining Materials for BASES I | 1d | Thu 10/22/26 | Thu 10/22/26 | 448455 | 462476 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
462 | Tech | Process | Process |  | LP | Receive Remaining Materials for BASES I | 1d | Fri 10/23/26 | Fri 10/23/26 | 461 | 464 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
463 | Tech | Process | Process | A | LP | Variants A BASES Product Prep | 35d | Tue 10/19/27 | Mon 12/6/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
464 | Tech | Process | Process |  | LP | Preview batch making for var A BASES I | 1w | Tue 10/19/27 | Mon 10/25/27 | 460462 | 465,466SS | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
465 | Tech | PR | PR |  | LP | Preview batch testing/stability for var A BASES I | 2w | Tue 10/26/27 | Mon 11/8/27 | 464 | 600601467478605 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
466 | Tech | Process | Process |  | LP | Create var A MFC's | 2w | Tue 10/19/27 | Mon 11/1/27 | 464SS | 484 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
467 | Tech | Process | Process |  | LP | Final product making for var A BASES I | 2w | Tue 11/9/27 | Mon 11/22/27 | 465 | 468818813 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
468 | Tech | PR | PR | A | LP | Final product testing for var A BASES I (approval, documents, etc) | 14ed | Mon 11/22/27 | Mon 12/6/27 | 467 | 478 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
469 | Tech | Process | Process | A | LP | Variants B BASES Product Prep | 30d | Mon 11/3/25 | Fri 12/12/25 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
470 | Tech | Process | Process |  | LP | Preview batch making for var B BASES I | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 471,472SS | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
471 | Tech | PR | PR |  | LP | Preview batch testing/stability for var B BASES I | 2w | Mon 11/10/25 | Fri 11/21/25 | 470 | 481600601473605 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
472 | Tech | Process | Process |  | LP | Create MFC's (for var B Only) | 2w | Mon 11/3/25 | Fri 11/14/25 | 470SS | 484 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
473 | Tech | Process | Process |  | LP | Final product making for var B BASES I | 1w | Mon 11/24/25 | Mon 12/1/25 | 471 | 474818813 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
474 | Tech | PR | PR | A | LP | Final product testing for var B BASES I (approval, documents, etc) | 11ed | Mon 12/1/25 | Fri 12/12/25 | 473 | 481 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
475 | Tech | PR | Process |  | LP | Packout Prep for BASES I | 310.5d? | Fri 10/23/26 | Fri 12/31/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
476 | Tech | PR | Process |  | LP | Receive Packing Materials | 146d? | Fri 10/23/26 | Thu 6/3/27 | 461 | 481478 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
477 | Tech | PR | Process |  | LP | Var A BASES Packing | 12.5d | Tue 12/7/27 | Thu 12/23/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
478 | Tech | PD | PR |  | LP | Pack-out Var A Product for BASES I | 1.5w | Tue 12/7/27 | Thu 12/16/27 | 465440468476 | 479481486 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
479 | Tech | PD | PR |  | LP | Micro var A Product for BASES I | 1w | Thu 12/16/27 | Thu 12/23/27 | 478 | 485 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
480 | Tech | PR | Process |  | LP | Var B BASES Packing | 8d | Thu 12/16/27 | Tue 12/28/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
481 | Tech | PD | PR |  | LP | Pack-out var B Product for BASES I | 3d | Thu 12/16/27 | Tue 12/21/27 | 471474478476 | 482487 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
482 | Tech | PD | PR |  | LP | Micro var B Product for BASES I | 1w | Tue 12/21/27 | Tue 12/28/27 | 481 | 485 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
483 | Tech | PR | PR |  | LP | BASES I Test Materials/ Clearance | 42.5d | Tue 11/2/27 | Thu 12/30/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
484 | Tech | PR | PR |  | LP | Submit SMART | 4w | Tue 11/2/27 | Mon 11/29/27 | 466472 | 485 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
485 | Tech | PR | PR | A | LP | Complete SMART | 2d | Tue 12/28/27 | Thu 12/30/27 | 482479484 | 487486 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
486 | Tech | PD | PR | A | LP | Product shipped for var A BASES I (put due date if needed based on contracts and agencies) | 1d | Thu 12/30/27 | Fri 12/31/27 | 478485 | 499 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
487 | Tech | PD | PR | A | LP | Product shipped for var B BASES I (put due date if needed based on contracts and agencies) | 1d | Thu 12/30/27 | Fri 12/31/27 | 485481 | 499 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
488 | Comm | Mktg | Mktg | A | LP | Concept Delivery for BASES I | 35d | Wed 12/2/26 | Wed 1/20/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
489 | Comm | A&I | A&I |  | LP | Conduct Client Objectives Meeting - Round 1 | 2d | Wed 12/2/26 | Fri 12/4/26 | 444FS+3.25mo | 492,490FS+3w | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
490 | Comm | A&I | A&I |  | LP | Conduct Client Objectives Meeting - Round 2 | 1d | Fri 12/25/26 | Mon 12/28/26 | 489FS+3w | 493FS+1w,494FS+1w,506FS+3w | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
491 | Comm | Mktg | Mktg |  | LP | Concept | 33d | Fri 12/4/26 | Wed 1/20/27 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
492 | Comm | A&I | A&I |  | LP | Draft Concept/After Use Questionnaire Delivered (3/30) | 7d | Fri 12/4/26 | Tue 12/15/26 | 489 | 495 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
493 | Comm | A&I | A&I |  | LP | Questions Finalized for Pre-Screening OQ Groups | 6d | Mon 1/4/27 | Tue 1/12/27 | 490FS+1w | 494 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
494 | Comm | A&I | A&I |  | LP | Pre- Screening OQ Groups | 6d | Tue 1/12/27 | Wed 1/20/27 | 490FS+1w,493 | 500 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
495 | Comm | Mktg | Mktg | A | LP | Final Concept/AU BASES I Questionnaire Input - Team | 16d | Tue 12/15/26 | Wed 1/6/27 | 492 | 496 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
496 | Comm | A&I | A&I |  | LP | Provide Final Concept/AU BASE II Questionnaire Feedback | 2d | Wed 1/6/27 | Fri 1/8/27 | 495,95 | 497 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
497 | Comm | A&I | A&I | A | LP | Final Concept/AU BASES I Questionnaire Approval - Susan/Beth | 4d | Fri 1/8/27 | Thu 1/14/27 | 496 | 503500 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
498 | Comm | A&I | A&I |  | LP | BASES I Execution | 30d | Fri 12/31/27 | Fri 2/11/28 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
499 | Comm | A&I | A&I |  | LP | BASES I Product Organized for Placement | 4d | Fri 12/31/27 | Thu 1/6/28 | 486487 | 500 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
500 | Comm | A&I | A&I |  | LP | BASES I Start Date (note date with agency)/Field Concept | 0d | Thu 1/6/28 | Thu 1/6/28 | 499494497 | 501 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
501 | Comm | A&I | A&I |  | LP | BASES Usage (end date with agency) | 2w | Thu 1/6/28 | Thu 1/20/28 | 500 | 502503 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
502 | Comm | A&I | A&I |  | LP | BASES I Concept Top Line (results expected date) | 1w | Thu 1/20/28 | Thu 1/27/28 | 501 | 509513512 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
503 | Comm | A&I | A&I |  | LP | Afteruse Field Start Date (date expected) | 5d | Thu 1/20/28 | Thu 1/27/28 | 501497 | 504 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
504 | Comm | A&I | A&I |  | LP | BASES I After Use Topline (date expected) | 11d | Thu 1/27/28 | Fri 2/11/28 | 503 | 509512603 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
505 | Comm | A&I | A&I | A | LP | BASES I Forecasting | 293d | Mon 1/18/27 | Thu 3/2/28 |  |  | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
506 | Comm | Mktg | Mktg | A | LP | Marketing Plan Inputs Final Decisions (date needed) | 1d | Mon 1/18/27 | Tue 1/19/27 | 490FS+3w | 507 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
507 | Comm | Mktg | Mktg | A | LP | Marketing Plan Alignment Meeting (date with agency) | 2d | Tue 1/19/27 | Thu 1/21/27 | 506 | 508 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
508 | Comm | Mktg | Mktg | A | LP | BASES I Building Model | 4w | Thu 1/21/27 | Tue 3/9/27 | 507 | 509512 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
509 | Comm | A&I | A&I |  | LP | BASES I Volume Topline to IBO (date expected) | 4d | Fri 2/11/28 | Thu 2/17/28 | 502504508 | 510511 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
510 | Comm | A&I | A&I | A | LP | BASES I IBO Turn Around and CMK Approval | 1w | Thu 2/17/28 | Thu 2/24/28 | 509 | 513 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
511 | Comm | Finance | Finance | A | LP | BASES I Financials | 1w | Thu 2/17/28 | Thu 2/24/28 | 509 | 513 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
512 | Comm | A&I | A&I |  | LP | BASES I Diagnostic Report/Tables (date expected) | 1w | Fri 2/11/28 | Fri 2/18/28 | 502504508 | 513 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
513 | Comm | A&I | A&I | A | LP | BASES I CMK Forecast Delivered (date expected) | 1w | Thu 2/24/28 | Thu 3/2/28 | 510511512502188 | 187,594,650,651,652,653,6 | New Package, New Formula, Commercial Concept/Sell-in | Design |  | Technical Scope | LP: BASES |  | LP: BASES
515 | Comm | A&I | A&I |  | LP | Define PC E&U CRP | 2w | Tue 8/4/26 | Mon 8/17/26 | 589591 | 516 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
516 | Comm | A&I | A&I |  | LP | Determine legs for PC E&U | 1w | Tue 8/18/26 | Mon 8/24/26 | 515 | 517 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
517 | Comm | A&I | A&I | A | LP | PC E&U CRP Approved | 0d | Mon 8/24/26 | Mon 8/24/26 | 516 | 518FF | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
518 | Comm | PD | PR | A | LP | Success Criteria Per Leg Locked for PC E&U | 24.8w | Tue 2/17/26 | Mon 8/24/26 | 517FF | 450,454,540FS+63d | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
519 | Tech | PR | PR | A | LP | Product Prep for PC E&U | 71d | Mon 11/16/26 | Mon 2/22/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
520 | Tech | PD | PD |  | LP | PC E&U Formulas defined and prelim testing | 37d | Mon 11/16/26 | Tue 1/5/27 |  |  |  | Design |  | Technical Scope | LP: E&U |  | LP: E&U
521 | Tech | PD | PD |  | LP | Model Formulas to Deliver Success Criteria | 37d | Mon 11/16/26 | Tue 1/5/27 |  |  |  | Design |  | Technical Scope | LP: E&U |  | LP: E&U
522 | Tech | PD | PD |  | LP | Complete All Variants Scope/Needs | 7.4w | Mon 11/16/26 | Tue 1/5/27 | 421 | 523SS+4w,526 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
523 | Tech | Process | Process |  | LP | Identify RM's needed for wide range of primary packs | 1d | Mon 12/14/26 | Mon 12/14/26 | 522SS+4w | 524 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
524 | Tech | PD | Process |  | LP | Order RM's/PMs for PC E&U | 3d | Tue 12/15/26 | Thu 12/17/26 | 523 | 525532 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
525 | Tech | PD | Process |  | LP | RM's Matls Received \ for PC E&U | 2w | Fri 12/18/26 | Thu 12/31/26 | 524 | 526 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
526 | Tech | PD | Process |  | LP | Preview batch making for PC E&U | 1w | Wed 1/6/27 | Tue 1/12/27 | 525522 | 527528 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
527 | Tech | PD | PR | A | LP | Preview batch testing for PC E&U (incl stability if applicable) | 2w | Wed 1/13/27 | Tue 1/26/27 | 526 | 529FS+2w,600,601,602,605 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
528 | Tech | PD | Process | A | LP | Create MFC's | 2w | Wed 1/13/27 | Tue 1/26/27 | 526 | 536 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
529 | Tech | PD | Process |  | LP | Final product making for PC E&U | 2d | Wed 2/10/27 | Thu 2/11/27 | 527FS+2w | 530602818813 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
530 | Tech | PD | PR | A | LP | Final product testing for PC E&U | 11ed | Thu 2/11/27 | Mon 2/22/27 | 529 | 533 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
531 | Tech | PR | Process |  | LP | Packout Prep for PC E&U | 178.5d | Fri 12/18/26 | Wed 8/25/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
532 | Tech | PR | Process |  | LP | Receive Packing Materials | 159d | Fri 12/18/26 | Wed 7/28/27 | 524 | 533 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
533 | Tech | PD | PR |  | LP | Pack-out Product for PC E&U | 1w | Thu 7/29/27 | Wed 8/4/27 | 530532 | 534 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
534 | Tech | PD | PR |  | LP | Micro Product for PC E&U (if applicable) | 1.5w | Thu 8/5/27 | Mon 8/16/27 | 533 | 538537 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
535 | Tech | PR | PR |  | LP | PC E&U Test Materials/ Clearance | 148.5d | Wed 1/27/27 | Mon 8/23/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
536 | Tech | PR | PR |  | LP | Submit SMART | 4w | Wed 1/27/27 | Fri 3/12/27 | 528 | 537 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
537 | Tech | PR | PR | A | LP | Complete SMART | 5d | Mon 8/16/27 | Mon 8/23/27 | 534536 | 538 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
538 | Tech | PR | PR | A | LP | Product shipped to agency for PC E&U | 2d | Mon 8/23/27 | Wed 8/25/27 | 534537 | 543 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
539 | Tech | PR | PR |  | LP | Product Placement | 225.5d | Thu 11/19/26 | Fri 10/1/27 |  |  | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
540 | Tech | PR | PR |  | LP | Concepts to agency for PC E&U | 0d | Thu 11/19/26 | Thu 11/19/26 | 518FS+63d | 541 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
541 | Tech | PR | PR |  | LP | E&U Questionnaire to P&G | 2d | Fri 11/20/26 | Mon 11/23/26 | 540 | 542 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
542 | Tech | PR | PR | A | LP | P&G Approval of E&U Questionnaire | 2d | Tue 11/24/26 | Wed 11/25/26 | 541 | 543 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
543 | Tech | PR | PR |  | LP | E&U Field Screener | 5d | Wed 8/25/27 | Wed 9/1/27 | 538542 | 544SS | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
544 | Tech | PR | PR |  | LP | E&U Packout/Product Placed | 2d | Wed 8/25/27 | Fri 8/27/27 | 543SS | 545 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
545 | Tech | PR | PR |  | LP | PC E&U Usage | 2w | Fri 8/27/27 | Fri 9/10/27 | 544 | 546 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
546 | Tech | PR | PR |  | LP | PC E&U Recall/Usage Questionnaire | 3w | Fri 9/10/27 | Fri 10/1/27 | 545 | 547 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
547 | Tech | PR | PR | A | LP | PC E&U Results Summary | 4w | Fri 10/1/27 | Fri 10/29/27 | 546 | 595 | New Package, New Formula | Design |  | Technical Scope | LP: E&U |  | LP: E&U
549 | Comm | A&I | A&I |  | LP | Kick off 3D Shelf Test Work | 6d | Fri 5/28/27 | Fri 6/4/27 | 364FS+25d | 550551 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
550 | Comm | IDM/A&I | A&I/IL | A | LP | Approve Scope and PACE | 1d | Mon 6/7/27 | Mon 6/7/27 | 549 | 564554556 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
551 | Comm | Sales | Sales |  | LP | Develop the Shelf POG’s 3D | 1.5d | Mon 6/7/27 | Tue 6/8/27 | 549 | 552 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
552 | Comm | Sales | Sales/Nate |  | LP | Decision for Footprints/Sizes for 3D Shelf Test | 1.5d | Tue 6/8/27 | Wed 6/9/27 | 551 | 553 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
553 | Comm | IDM/Sales | IL/Sales | A | LP | Lock Control Shelf POG’s and label spots/develop SKU list/number coding | 0d | Wed 6/9/27 | Wed 6/9/27 | 552 | 555 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
554 | Comm | Sales | Sales/Sales | A | LP | Lock New Modular POG's | 1w | Tue 6/8/27 | Mon 6/14/27 | 550 | 555 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
555 | Comm | Mktg | Mktg |  | LP | Decision for SKUs for 3D Shelf Test – complete SKU list/number coding document | 3d | Tue 6/15/27 | Thu 6/17/27 | 553554 | 558 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
556 | Comm | A&I | Sales |  | LP | Draft Shelf Test | 2w | Tue 6/8/27 | Mon 6/21/27 | 550 | 564 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
557 | Comm | A&I | A&I |  | LP | Get Product for 3D Shelf Test R2 | 17d | Thu 6/17/27 | Mon 7/12/27 |  |  | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
558 | Comm | A&I | A&I |  | LP | Send list of existing primary packaging needed to PS reps | 0d | Thu 6/17/27 | Thu 6/17/27 | 555 | 559560561 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
559 | Comm | MPD | MPD |  | LP | Obtain new primary packages (new color/new sizes) | 3w | Fri 6/18/27 | Thu 7/8/27 | 558 | 562 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
560 | Comm | MPD | MPD |  | LP | Obtain existing primary packaging | 2w | Fri 6/18/27 | Thu 7/1/27 | 558 | 562 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
561 | Comm | Design | Design |  | LP | Generate Labels for new Primary Package | 2d | Fri 6/18/27 | Mon 6/21/27 | 558 | 562 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
562 | Comm | Design | Design |  | LP | Send list of existing primary packaging needed to PS reps | 2d | Fri 7/9/27 | Mon 7/12/27 | 559560561 | 563 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
563 | Comm | Design | Design |  | LP | Obtain new primary packages (new color/new sizes) | 0d | Mon 7/12/27 | Mon 7/12/27 | 562 | 566 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
564 | Comm | A&I | A&I |  | LP | Obtain existing primary packaging | 2d | Tue 6/22/27 | Wed 6/23/27 | 550556 | 565 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
565 | Comm | A&I | A&I | A | LP | Generate Labels for new Primary Package | 2d | Thu 6/24/27 | Fri 6/25/27 | 564 | 566 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
566 | Comm | A&I | A&I/A&I |  | LP | Conduct Test BRIC Shelf Test/Quals | 14d | Tue 7/13/27 | Fri 7/30/27 | 563565 | 567 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
567 | Comm | A&I | A&I/A&I | A | LP | Results BRIC Shelf Test/Quals | 0d | Fri 7/30/27 | Fri 7/30/27 | 566 | 568,222FS-1w,212FS+2w | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
568 | Comm | Sales | Sales |  | LP | Lead package commercially qualified | 1d | Mon 8/2/27 | Mon 8/2/27 | 567 | 668 | New Artwork, New Package, New Brand Architecture | Design |  | Technical Scope | LP: 3D Shelf Test |  | LP: 3D Shelf Test
571 | Tech | Process | Process | A |  | Technical learning plan updated (need to plug in some items from DTRM here) | 2w | Mon 7/27/26 | Mon 8/10/26 | 588114 | 572577575 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
572 | Tech | PD | Process |  |  | GTRO/dTRM update to get to ready to invest | 2w | Tue 8/11/26 | Tue 8/25/26 | 571 | 583 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
573 | Tech | PR | PR |  |  | Freedom to Practice issues identified/resolved & execute IP strategy | 2w | Mon 2/9/26 | Fri 2/20/26 | 114 | 583 | All | Design |  | All | Mandatory |  | Technical Readiness
574 | Tech | Process | Process |  |  | TFS finalized | 2w | Fri 1/28/28 | Thu 2/10/28 | 118,603FF-1mo | 792583 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
575 | Tech | PR | PR |  |  | QEC expanded | 2w | Tue 8/11/26 | Mon 8/24/26 | 121571 | 809583 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
576 | Tech | Process | Process |  |  | Process flowchart final | 1w | Tue 3/14/28 | Mon 3/20/28 | 119,836SS,583 | 792 | All | Design |  | Technical Scope | Formula |  | Technical Readiness
577 | Tech | Eng | Eng/Eng |  |  | Initiative Start-up (ISU) risk assessment #1 | 1w | Tue 3/14/28 | Mon 3/20/28 | 571583 | 795665578 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
578 | Tech | Eng | Eng/Eng |  |  | Initiative Start Up risk assessment #2 | 1d | Tue 3/21/28 | Tue 3/21/28 | 847577583 | 665 | All | Design |  | Technical Scope | Mandatory | Ready to Invest/Commit | Technical Readiness
579 | Tech | Eng | Eng/Eng |  |  | Overall Risk Assessment (ORA) develop/update | 2w | Fri 12/31/27 | Thu 1/13/28 | 847 | 583 | All | Design |  | Technical Scope | Mandatory |  | Technical Readiness
580 | Tech | Eng | Eng/Eng |  |  | Checklist Based Design Review (CBDP) | 2w | Fri 12/24/27 | Thu 1/6/28 | 847SS | 793,794,598FF-90ed | All | Design |  | Technical Scope | Mandatory | Ready to Invest/Commit | Technical Readiness
581 | Tech | Mktg | Mktg |  |  | Patent design Trademark application complete | 60d | Mon 1/26/26 | Mon 4/20/26 | 114SS | 583 | All | Design |  | All | Mandatory |  | Technical Readiness
582 | All | IDM | IL |  |  | Risk Assumptions & agreements documented | 1w | Mon 3/30/26 | Fri 4/3/26 | 61,172,88,89,193 | 583 | Risk Assessment | Design |  | All | Mandatory |  | Technical Readiness
583 | All | TRO | TRL | A |  | Technical scope locked | 1mo | Fri 2/11/28 | Mon 3/13/28 | 582,120,172,88,89,193,208,572,573,574,579,581,631,637,639,575 | 163576577578 | Eng Scope, New Package, New Formula | Design |  | Technical Scope | Mandatory | Ready to Invest/Commit | Technical Readiness
587 | Tech | PR | TRL | A |  | Define Product Strategy/Technical Design Frozen | 0d | Fri 7/17/26 | Fri 7/17/26 | 120121111 | 588 | New Formula | Design |  | Technical Scope | Formula
588 | Tech | PR | PR | A |  | Define Success Criteria | 1w | Mon 7/20/26 | Fri 7/24/26 | 587 | 589590591571 | New Formula | Design |  | Technical Scope | Formula
589 | Tech | PR | PR |  | LP | Develop Draft Scope for CUC (select variants) | 1d | Mon 7/27/26 | Mon 7/27/26 | 588 | 515407 | New Formula | Design |  | Commercial Facing | LP: CUC |  | LP: CUC
590 | Tech | PR | PR |  | LP | Develop Draft Scope for BASES I | 1w | Mon 7/27/26 | Mon 8/3/26 | 588 | 442 | New Formula | Design |  | Commercial Facing | LP: BASES |  | LP: BASES
591 | Tech | PR | PR |  | LP | Develop Draft Scope for PC E&U | 1w | Mon 7/27/26 | Mon 8/3/26 | 588 | 515 | New Formula | Design |  | Commercial Facing | LP: E&U |  | LP: E&U
593 | Tech | PR | TRL | A | LP | Approve CUC results | 0d | Wed 1/27/27 | Wed 1/27/27 | 440 | 663603815 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: CUC |  | LP: CUC
594 | Tech | PR | TRL | A | LP | Approve BASES II results | 4d | Thu 3/2/28 | Wed 3/8/28 | 513647 | 663603815698 | New Artwork, New Package, New Brand Architecture | Design |  | Commercial Facing | LP: BASES |  | LP: BASES
595 | Tech | PR | TRL | A | LP | Approve PC E&U results | 4d | Fri 10/29/27 | Thu 11/4/27 | 547647 | 663603815698 | New Formula | Design |  | Commercial Facing | LP: E&U |  | LP: E&U
596 | Tech | Formula | PD | A |  | Complete formula definition for all non-consumer tested formulas (list variants) | 1w | Mon 9/27/27 | Mon 10/4/27 | 598SF | 698603 | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Lock Form
597 | Tech | Formula | PD | A |  | Complete formula definition for any variant that needs requalification | 0d | Fri 11/13/26 | Fri 11/13/26 | 457 | 7.9864e+20 | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Lock Form
598 | Tech | Process | Process |  |  | Place non consumer tested formulas in stability | 1w | Mon 10/4/27 | Fri 10/8/27 | 580FF-90ed | 596SF | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Lock Form
600 | Tech | Process | Process |  |  | 6 wks read | 42ed | Mon 11/8/27 | Mon 12/20/27 | 448465527471 | 601 | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Stability
601 | Tech | Process | Process |  |  | 12 wks read | 84ed | Mon 12/20/27 | Mon 3/13/28 | 448465527471600 | 603 | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Stability
602 | Tech | Process | Process |  |  | Stability suds | 90ed | Thu 2/11/27 | Wed 5/12/27 | 448527529 | 603818 | New Formula | Design |  | Technical Scope | Formula |  | TR: Prod: Stability
603 | Tech | Process | Process |  |  | Preliminary formula card | 0d | Mon 3/13/28 | Mon 3/13/28 | 5.9359e+23 | 798,641,642,643,824,574FF-1mo | New Formula | Design |  | Technical Scope | Formula | Ready to Invest | TR: Prod: Stability
605 | Comm | Mktg | Mktg | A |  | Initial Preview batch performance/success criteria documentation | 1d | Tue 11/9/27 | Tue 11/9/27 | 527471465 | 606 | New Formula, New Claims | Design |  | Technical Scope | Formula, Claims |  | TR: Claims Support
606 | Comm | Mktg/ PR | Mktg/ PR | A |  | Initial POC approval of performance/success criteria documentation | 1w | Wed 11/10/27 | Tue 11/16/27 | 605 | 607SS | New Formula, New Claims | Design |  | Technical Scope | Formula, Claims |  | TR: Claims Support
607 | Comm | Mktg/ PR | Mktg/ PR | A |  | Initial Approval of direction of Claims using success criteria | 1w | Wed 11/10/27 | Tue 11/16/27 | 606SS | 686789373 | New Formula, New Claims | Design |  | Technical Scope | Formula, Claims |  | TR: Claims Support
610 | Tech | Pkg Dev | Finance |  |  | Issue PO for Pilot/Prototype Program | 6d | Fri 1/30/26 | Fri 2/6/26 | 126FS+1w | 612 | New Package | Design |  | Technical Scope | Package | Ready for Early Invest | TR: Package Ready
612 | Tech | Pkg Dev | Pkg Dev |  |  | Drawing & 3D Model | 39.5d | Mon 7/6/26 | Thu 9/10/26 | 405SF+6d,610 | 613 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
613 | Tech | Pkg Dev | Pkg Dev |  |  | Complete M&S/Sign off on DIA for all new Primary Packs | 64.5d | Fri 9/11/26 | Fri 12/11/26 | 612 | 614 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
614 | Tech | Pkg Dev | Pkg Dev |  |  | Primary Pack Unit Cavity Builds | 42.5d | Fri 12/11/26 | Thu 2/11/27 | 613 | 615 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
615 | Tech | Pkg Dev | Pkg Dev |  |  | Unit Cavity Trials / Qualification | 120d | Fri 2/12/27 | Wed 8/18/27 | 614 | 616 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
616 | Tech | Pkg Dev | Pkg Dev |  |  | Unit Runs | 34d | Thu 8/19/27 | Tue 10/5/27 | 615 | 617630638639 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
617 | Tech | Pkg Dev | Pkg Dev |  |  | Unit Run / Fresh & Aged Data | 1w | Wed 10/6/27 | Tue 10/12/27 | 616 | 618 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
618 | Tech | Pkg Dev | Pkg Dev |  |  | ESCR & Fill Trials | 2w | Wed 10/13/27 | Tue 10/26/27 | 617 | 619620 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
619 | Tech | Pkg Dev | Pkg Dev |  |  | Ship Stack / P&G 5M | 3.8w | Wed 10/27/27 | Mon 11/22/27 | 618 | 620 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Dev Qual-Prod
620 | Tech | Pkg Dev | Pkg Dev | A |  | Production Tool Approval | 7d | Tue 11/23/27 | Wed 12/1/27 | 619618 |  | New Package | Design |  | Technical Scope | Package | Ready to Invest/Commit | TR: Pack Dev Qual-Prod
623 | Tech | Pkg Dev | MPD |  |  | Develop specs for new pkg mtl | 2w | Mon 11/3/25 | Fri 11/14/25 |  | 628,624SS | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
624 | Tech | Purchasing | PUR |  |  | Work with Purchasing to confirm supplier for pkg mtl needed (incl. timing, specs, substrate, etc) | 1mo | Mon 11/3/25 | Tue 12/2/25 | 623SS | 627625 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
625 | Tech | Purchasing | PUR |  |  | Set up new supplier Aravo - inluding Legal Entity and all vendor locations and all MEP/SEP generated | 1w | Wed 12/3/25 | Tue 12/9/25 | 624 | 626 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
626 | Tech | Purchasing | PUR |  |  | Develop specs for New packing material with supplier - 80/20 in Enovia including MEP/SEP | 1w | Wed 12/10/25 | Tue 12/16/25 | 625 | 627 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
627 | Tech | Design | Agency |  | LP | Provide supplier with artwork for BASES/3D BISI-P | 1w | Wed 12/17/25 | Tue 12/23/25 | 624626 | 628 | New Package | Design |  | Technical Scope | LP: BASES-3D BISIP |  | TR: Pack Matl
628 | Tech | Mktg | Mktg |  |  | Review & approve pkg mtg specs/stds | 1w | Wed 12/24/25 | Tue 12/30/25 | 623627 | 629805 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
629 | Tech | Pkg Dev | MPD |  |  | Supplier to deliver pkg mtl or prototype (incl production and delivery) | 5w | Wed 12/31/25 | Tue 2/3/26 | 628 | 630805 | New Package | Design |  | Technical Scope | Package |  | TR: Pack Matl
630 | Tech | Pkg Dev | Finance |  | LP | Assemble FINAL pkg mtl for BASES/3D BISI-P | 1w | Wed 10/6/27 | Tue 10/12/27 | 629616 | 631 | New Package, Commercial Toolkit/Sell-in | Design |  | Commercial Facing | LP: BASES-3D BISIP |  | TR: Pack Matl
631 | Tech | Pkg Dev | Finance | A | LP | Ship pkg mtl for BASES/3D-BISIP | 2d | Wed 10/13/27 | Thu 10/14/27 | 630 | 459361583 | New Package, Commercial Toolkit/Sell-in | Design |  | Commercial Facing | LP: BASES-3D BISIP |  | TR: Pack Matl
633 | Tech | Eng | Eng | A |  | 30% Design Basis Development & Sign-off | 7w | Fri 8/28/26 | Fri 10/30/26 | 33FS+3mo | 846 | Package | Design |  | Technical Scope | Package |  | TR: Pkg Lines
634 | Tech | Eng | Eng |  |  | Lead Line Determination | 1w | Fri 12/10/27 | Thu 12/16/27 | 846FF | 813 | Package | Design |  | Technical Scope | Package |  | TR: Pkg Lines
636 | Tech | Eng | Eng |  |  | Qualify Machine Quality with New Relevant Transformations | 6w | Mon 11/3/25 | Mon 12/15/25 |  | 637 | Package | Design |  | Technical Scope | Package |  | TR: Pkg Lines
637 | Tech | Eng | Eng |  |  | Approval of Transformations | 4w | Tue 12/16/25 | Mon 1/12/26 | 636 | 583 | Package | Design |  | Technical Scope | Package |  | TR: Pkg Lines
638 | Tech | Eng | Eng |  |  | Run Macro Trials at Labs/Sites - Round 1 | 2mo | Wed 10/6/27 | Mon 12/6/27 | 616 | 639 | Package | Design |  | Technical Scope | Package |  | TR: Pkg Lines
639 | Tech | Eng | Eng |  |  | Run Macro Trials at Labs/Sites - Round 2 | 3d | Tue 12/7/27 | Thu 12/9/27 | 616638 | 848,847,846,42SS,583 | Package | Design |  | Technical Scope | Package | Ready to Invest | TR: Pkg Lines
641 | Tech | MPD | Scott |  |  | Material Supplier FMECA & TFS | 1w | Tue 3/14/28 | Mon 3/20/28 | 668FS-3w,603,597,122 | 798 | Formula, Package, Supplier | Design |  | Technical Scope | Formula, Package, Supplier |  | TR: SC Readiness
642 | Tech | SNO | MSM TBD | A |  | Confirm material supply usage/availability | 1w | Tue 3/14/28 | Mon 3/20/28 | 603597122 | 918919920 | Formula, Package, Supplier | Design |  | Technical Scope | Formula, Package, Supplier |  | TR: SC Readiness
643 | Tech | SNO | Joel | A |  | Agreement with Supply Network design (Mat'l Delivery Strategy) | 1w | Tue 3/14/28 | Mon 3/20/28 | 668603597122 | 791 | Formula, Package, Supplier | Design |  | Technical Scope | Formula, Package, Supplier |  | TR: SC Readiness
644 | Tech | SNO | MSM TBD | A |  | Supplier base capability/reliability - High Level Analysis | 4w | Mon 6/15/26 | Thu 7/16/26 | 122 | 645FF,921,922 | Formula, Package, Supplier | Design |  | Technical Scope | Formula, Package, Supplier |  | TR: SC Readiness
645 | Tech | SNO | MSM TBD | A |  | Formulate strategy for PtD time inventory cost | 4w | Mon 6/15/26 | Thu 7/16/26 | 644FF,122 |  | Formula, Package, Supplier | Design |  | Technical Scope | Formula, Package, Supplier |  | TR: SC Readiness
647 | All | Finance | Finance |  |  | Commercial and Financial Assessment of New SKU's | 3w | Thu 9/24/26 | Wed 10/14/26 | 405 | 594595163 | Commercial Concept/Sell-in | Design |  | Commercial Facing | Formula, Package |  | PC: Financials
650 | Comm | A&I | A&I | A |  | Detailed Forecast (SIMPL red sheet) | 0d | Thu 3/9/28 | Thu 3/9/28 | 513187 | 655,656,657,658,5 | All | Design |  | All | Mandatory | Ready to Invest/Commit | PC: Fin: Volume
651 | Comm | A&I | A&I |  |  | Awareness, Trial / Penetration | 0d | Thu 3/2/28 | Thu 3/2/28 | 513 | 655,656,657,658,5 | Commercial Concept/Sell-in | Design |  | Commercial Facing | Mandatory | Ready to Invest/Commit | PC: Fin: Volume
652 | Comm | A&I | A&I |  |  | Cannibalization | 0d | Thu 3/2/28 | Thu 3/2/28 | 513 | 655,656,657,658,5 | Commercial Concept/Sell-in | Design |  | Commercial Facing | Mandatory | Ready to Invest/Commit | PC: Fin: Volume
653 | Comm | A&I | A&I | A |  | Source of Volume Analysis | 0d | Thu 3/2/28 | Thu 3/2/28 | 513188 | 655,656,657,658,5 | Commercial Concept/Sell-in | Design |  | Commercial Facing | Mandatory | Ready to Invest/Commit | PC: Fin: Volume
655 | Comm | Finance | Finance | A |  | SIMPL Financial Fact Sheet | 1w | Thu 3/9/28 | Thu 3/16/28 | 650651652653 | 659 | All | Design |  | All | Mandatory |  | PC: Fin: Assump
656 | Comm | Finance | Finance | A |  | Gross and Incremental NOS, DOPAT | 1w | Thu 3/9/28 | Thu 3/16/28 | 650651652653 | 659 | All | Design |  | All | Mandatory |  | PC: Fin: Assump
657 | Comm | Finance | Finance | A |  | Gross Margin | 1w | Thu 3/9/28 | Thu 3/16/28 | 650651652653 | 659 | All | Design |  | All | Mandatory |  | PC: Fin: Assump
658 | Comm | Finance | Finance | A |  | NPV | 1w | Thu 3/9/28 | Thu 3/16/28 | 650651652653 | 659 | All | Design |  | All | Mandatory |  | PC: Fin: Assump
659 | Comm | Finance | Finance | A |  | Business model & pricing | 1w | Thu 3/16/28 | Thu 3/23/28 | 166655656657658 | 664672 | All | Design |  | All | Mandatory |  | PC: Fin: Assump
661 | Comm | Finance | Jenny |  |  | Capital Estimate Complete | 8w | Thu 12/23/27 | Wed 2/16/28 | 145,668FF | 664932 | Formula, Package, Eng Scope | Design |  | Technical Scope | Formula, Package, Eng Scope |  | PC: Fin: Cost
662 | Supply | SNO | Kelvin |  |  | Transition Costs estimate complete | 2w | Thu 4/27/28 | Wed 5/10/28 | 192 | 664931 | All | Design |  | All | Formula, Package, Eng Scope |  | PC: Fin: Cost
663 | Comm | Finance | Jenny |  |  | Formula cost estimate complete | 2mo | Wed 3/8/28 | Tue 5/9/28 | 593594595 | 664933 | Formula | Design |  | Technical Scope | Formula |  | PC: Fin: Cost
664 | Comm | Finance | Finance | A |  | Update Financial Analysis for PC | 1d | Thu 5/11/28 | Thu 5/11/28 | 659661663662 | 666 | All | Design |  | All | Mandatory |  | PC: Fin: Cost
666 | Comm | Mktg | Mktg | A |  | Update Commercial PC documents | 1d | Fri 5/12/28 | Fri 5/12/28 | 664 | 12FS+3d | Commercial Facing | Design |  | Commercial Facing | Mandatory |  | PC: Fin: Comm Costs
668 | Comm | Pkg Dev | MPD | A |  | Package design locked | 1w | Thu 2/10/28 | Wed 2/16/28 | 392568405 | 641FS-3w,643,661FF,736FS+1.5mo | Package | Design |  | Technical Scope | Package |  | PC: Project Specific
672 | Comm | Sales | IL |  |  | Pricing final | 2w | Thu 3/23/28 | Thu 4/6/28 | 659,5 | 673 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
673 | Comm | Sales | Sales |  |  | Customer plans in place for DPSM (Distribution, Pricing, Shelving, Merchandising)/MDA | 3mo | Thu 4/6/28 | Fri 7/7/28 | 672186683 | 6.7568e+17 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
674 | Comm | Sales | Sales |  |  | Update CVA | 3w | Fri 7/7/28 | Fri 7/28/28 | 673 | 675 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
675 | Comm | Sales | Sales |  |  | Price List Order Guide (PLOG) data updated | 8w | Fri 7/28/28 | Fri 9/22/28 | 673,5,674 | 679 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
676 | Comm | Sales | Sales |  |  | Plan Letter in place | 8w | Fri 7/7/28 | Fri 9/1/28 | 673,5 | 677 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
677 | Comm | Sales | Sales |  |  | Presentations (GBU, Multi GBU, Retail) | 2w | Fri 9/1/28 | Fri 9/15/28 | 676,5 | 679 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
678 | Comm | Sales | Sales |  |  | By channel financial & demand plans linked (BU & MO) | 6w | Fri 7/7/28 | Fri 8/18/28 | 673,5 | 679975976 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
679 | Comm | Sales | Sales |  |  | Finalize GBP(field release) materials | 28d | Fri 9/22/28 | Wed 11/1/28 | 678,677,5,675 | 694,21 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
680 | Comm | Mktg | Mktg |  |  | Commercial IP strategy final (FTP approved) | 1mo | Thu 3/9/28 | Mon 4/10/28 | 168,5,116 | 945 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Customer Selling
682 | Comm | Sales | Sales | A |  | Initiate Data Entry Form (DEF) | 1.5mo | Fri 7/7/28 | Wed 8/23/28 | 171SS,673,160,161,162 |  | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Release to Field
683 | Comm | Sales | Sales | A |  | Update Shopper Based Design | 2w | Fri 2/5/27 | Thu 2/18/27 | 167355206 | 673 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | MR: Release to Field
685 | Comm | Mktg | Eng |  |  | Updates Marketing Plans Based on Pre-Table Top | 1w | Tue 10/13/26 | Mon 10/19/26 | 284 | 724,734,691,692,693,688,731,706FS-4w | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
686 | Comm | Mktg | Eng |  |  | Legal concurrence of Mktg (final) MNI | 2w | Thu 5/4/28 | Thu 5/18/28 | 607701 | 724734731726706 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
687 | Comm | A&I | Kristy |  |  | TPA complete (to incl. trial plans) | 1w | Thu 3/9/28 | Thu 3/16/28 | 5208 | 694945 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
688 | Comm | Mktg | Eng |  |  | Leverage plan approved | 4w | Thu 3/9/28 | Thu 4/6/28 | 5685 | 694 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
689 | Comm | Mktg | Eng | A |  | Tabletop approved | 7d | Mon 7/17/28 | Wed 7/26/28 | 7.2473e+32 | 694696945695 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
691 | Comm | Mktg | Mktg |  |  | Country XX | 1w | Tue 10/20/26 | Mon 10/26/26 | 685 | 732689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
692 | Comm | Mktg | Mktg |  |  | Country XX | 1w | Tue 10/20/26 | Mon 10/26/26 | 685 | 689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
693 | Comm | Mktg | Mktg |  |  | Country XX | 1w | Tue 10/20/26 | Mon 10/26/26 | 685 | 689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
694 | Comm | Sales | Sales |  |  | MRAT Completed w/MDO | 0d | Wed 11/1/28 | Wed 11/1/28 | 689679687688 | 21 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
695 | Comm | Mktg | Eng |  |  | Initiative toolbox element complete | 1d | Wed 7/26/28 | Thu 7/27/28 | 207689 | 945 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Mktg Plans
696 | Comm | A&I | Kristy |  |  | Initiative tracker set-up | 1d | Wed 7/26/28 | Thu 7/27/28 | 689 | 945 | All | Qualify & Ready |  | All | Mandatory |  | CR: Mktg Plans
698 | Comm | PR | PR |  |  | Product Available for R1 POCs (multiple rounds if needed) | 0d | Wed 3/8/28 | Wed 3/8/28 | 594595596457 | 700 | Claims | Qualify & Ready |  | Commercial Facing | Claims |  | CR: Claims
699 | Comm | Mktg | Eng |  |  | R1 Claims Chosen | 0d | Fri 10/29/27 | Fri 10/29/27 | 220 | 700 | Claims | Qualify & Ready |  | Commercial Facing | Claims |  | CR: Claims
700 | Comm | PR | PR |  |  | POC testing R1 (all proposed) | 8w | Wed 3/8/28 | Wed 5/3/28 | 699698 | 701758 | Claims | Qualify & Ready |  | Commercial Facing | Claims |  | CR: Claims
701 | Comm | Mktg | Eng |  |  | Claim Legal Approval R1 | 1d | Wed 5/3/28 | Thu 5/4/28 | 700789 | 686702808 | Claims | Qualify & Ready |  | Commercial Facing | Claims |  | CR: Claims
702 | Comm | Mktg | Eng |  |  | Obtain NACS (Claim Number) R1 | 2d | Thu 5/4/28 | Mon 5/8/28 | 701 | 766689 | Claims | Qualify & Ready |  | Commercial Facing | Claims |  | CR: Claims
706 | Comm | Mktg | Saatchi |  |  | Pre-Pro (award/pre-pro/dig production) | 0d | Thu 5/18/28 | Thu 5/18/28 | 5,284FS-2w,685FS-4w,686,278 | 707 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
707 | Comm | Mktg | Saatchi |  |  | Round 1 Review | 0d | Thu 5/18/28 | Thu 5/18/28 | 706 | 708 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
708 | Comm | Mktg | Saatchi |  |  | Round 2 Review | 0d | Thu 5/18/28 | Thu 5/18/28 | 707 | 710 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
710 | Comm | Mktg | Saatchi |  |  | In Field Testing (GM & USH) | 5w | Thu 5/18/28 | Thu 6/22/28 | 708 | 711 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
711 | Comm | Mktg | Saatchi |  |  | Test 1 Results | 1d | Thu 6/22/28 | Fri 6/23/28 | 710 | 712 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
712 | Comm | Mktg | Saatchi |  |  | Revisions | 1w | Fri 6/23/28 | Fri 6/30/28 | 711 | 713689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
713 | Comm | Mktg | Saatchi |  |  | Approve Final Direction for Full-up Production/GBP | 0d | Fri 6/30/28 | Fri 6/30/28 | 712 | 689949950951 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
715 | Comm | PR | PR |  |  | PDD/Garment Brief Alignment | 1w | Wed 9/9/26 | Tue 9/15/26 | 278 | 716 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
716 | Comm | PR | PR |  |  | Conduct Garment Search | 1w | Wed 9/16/26 | Tue 9/22/26 | 715 | 717 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
717 | Comm | PR | PR |  |  | Conduct Garment Test | 4w | Wed 9/23/26 | Tue 10/20/26 | 716 |  | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
718 | Comm | Mktg | Saatchi |  |  | Pre-bid/Bid/Award | 3w | Wed 9/9/26 | Tue 9/29/26 | 278 | 719 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
719 | Comm | Mktg | Saatchi |  |  | Prep/Scout/Cast/Set Design/Wardrobe | 3w | Wed 9/30/26 | Tue 10/20/26 | 718 | 720 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
720 | Comm | Mktg | Saatchi |  |  | Pre-pro Meeting/Shoot | 4w | Wed 10/21/26 | Tue 11/17/26 | 719 | 721 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
721 | Comm | Mktg | Saatchi |  |  | Edit/Agency Approvals/Revisions | 1.5w | Wed 11/18/26 | Fri 11/27/26 | 720 | 722 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
722 | Comm | Mktg | Saatchi |  |  | Present Rough Cuts | 0d | Fri 11/27/26 | Fri 11/27/26 | 721 | 723949950951 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: TV Plans
723 | Comm | Mktg | Saatchi |  |  | Approval/Finish (tie to field) | 1.5w | Fri 11/27/26 | Tue 12/8/26 | 722 | 6 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory | Ready to Release | CR: Init TB: TV Plans
724 | Comm | Mktg | Saatchi |  |  | Print Plans | 3w | Thu 5/18/28 | Thu 6/8/28 | 279284685686 | 689952 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Print
726 | Comm | Mktg | Saatchi |  |  | Digital Objectives and Strategy | 2w | Thu 5/18/28 | Thu 6/1/28 | 280,284FS-4w,686 | 727 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Digital
727 | Comm | Mktg | Saatchi |  |  | Menu of Executions (Websites, online ads, mobile ads etc.) | 2w | Thu 6/1/28 | Thu 6/15/28 | 726 | 728729 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Digital
728 | Comm | Mktg | Saatchi |  |  | Search Guidelines | 1mo | Thu 6/15/28 | Mon 7/17/28 | 727 | 689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Digital
729 | Comm | Mktg | Saatchi |  |  | iMedia Guidelines | 1mo | Thu 6/15/28 | Mon 7/17/28 | 727 | 689954955956 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Digital
731 | Comm | A&I | A&I |  | LP | InStore Plans Qualified | 2w | Thu 5/18/28 | Thu 6/1/28 | 281284685686 | 732 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: In Store
732 | Comm | Mktg | Mktg |  |  | Confirm InStore Claims Are Approved by Legal | 2w | Thu 6/1/28 | Thu 6/15/28 | 691731 | 689733 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: In Store
733 | Comm | Mktg | Mktg | A |  | In Store Plans Released for Retailer Engagement | 3d | Thu 6/15/28 | Tue 6/20/28 | 732 | 957 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: In Store
734 | Comm | Mktg | Mktg | A | LP | Media Plans | 3w | Thu 5/18/28 | Thu 6/8/28 | 282284685686 | 689 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Manadatory |  | CR: Init TB: Media
736 | Supply | PR | PR |  |  | Final Proof of Claim Ready - temporary | 1d | Tue 4/4/28 | Tue 4/4/28 | 668FS+1.5mo | 737 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
737 | Supply | Design | Design |  |  | Finalize name & designs | 1.5w | Wed 4/5/28 | Fri 4/14/28 | 736 | 738SS+1w,739 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
738 | Supply | Design | Design |  |  | Design Planning Meeting-Print Feasibility | 1d | Wed 4/12/28 | Wed 4/12/28 | 737SS+1w | 739 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
739 | Supply | Design | Design |  |  | Final Review- w/ GM- Approval | 1d | Fri 4/14/28 | Mon 4/17/28 | 738737 | 740742 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
740 | Supply | Design | Design |  |  | DESIGN LOCK - Final Package to all Variants with Final Claims | 26d | Mon 4/17/28 | Tue 5/23/28 | 739 | 754763 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
742 | Comm | Design | Design |  |  | Agreed to Label Design | 0d | Mon 4/17/28 | Mon 4/17/28 | 739 | 743 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
743 | Comm | Design | Design |  |  | Agreed to Test Substrates/SKUS/Finishes | 0d | Mon 4/17/28 | Mon 4/17/28 | 742 | 744 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
744 | Comm | Design | Design |  |  | Separations/Print Tools | 2w | Mon 4/17/28 | Mon 5/1/28 | 743 | 745 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
745 | Comm | Design | Design |  |  | Run new Labels/Bottles | 3w | Mon 5/1/28 | Mon 5/22/28 | 744 | 746 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
746 | Comm | Design | Design |  |  | Final Approval of Locked Substrates and Finishes | 0d | Mon 5/22/28 | Mon 5/22/28 | 745 | 754763 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
748 | Supply | PS | Eng/IOL |  |  | Create Completed POA list | 2d | Tue 4/4/28 | Wed 4/5/28 | 164 | 749 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
749 | Supply | Mktg | Eng |  |  | Submit PDR's in EPadex (enter BC's/POAs) | 1w | Thu 4/6/28 | Wed 4/12/28 | 748160161162 | 750SS | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
750 | Supply | PS | AW |  |  | Artwork Alignment Meeting (DPM Mtg) | 1d | Thu 4/6/28 | Thu 4/6/28 | 749SS | 751 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
751 | Supply | PS | AW |  |  | Approve PDR in EPadex | 3d | Fri 4/7/28 | Tue 4/11/28 | 750 | 752 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
752 | Supply | MPD | Scott |  |  | Provide TD in illustrator format to SGS (UC cap only new item), Approved TD | 10d | Wed 4/12/28 | Fri 4/28/28 | 751 | 754763 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
754 | Supply | Design | Design |  |  | Agency Upload GOS to Epadex | 5d | Tue 5/23/28 | Tue 5/30/28 | 752740746 | 755,763FS+5d | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
755 | Supply | Mktg | Eng | A |  | Graphic Options Approval in Epadex (DCIC) | 2d | Tue 5/30/28 | Thu 6/1/28 | 754 | 757758 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
757 | Comm | Artwork | AW |  |  | Color development (assume 8 unique designs) | 5d | Thu 6/1/28 | Thu 6/8/28 | 755 | 759 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
758 | Comm | Mktg | Eng |  |  | Master Copy Meeting- w/Legal - legal number for master copy | 1d | Thu 6/1/28 | Fri 6/2/28 | 755700 | 759 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
759 | Comm | Mktg | Eng |  |  | Master Copy approval - all waves (MF mtg) | 2d | Thu 6/8/28 | Mon 6/12/28 | 757758 | 760SS | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
760 | Comm | Mktg | Eng |  |  | Upload Master Copy | 2d | Thu 6/8/28 | Mon 6/12/28 | 759SS | 761 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
761 | Supply | Artwork | AW |  |  | Wave 1 - Approval | 3w | Mon 6/12/28 | Mon 7/3/28 | 760 | 959805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
763 | Comm | Design | Design |  |  | Agency Upload GOS to Epadex | 10d | Tue 6/6/28 | Tue 6/20/28 | 752,740,746,754FS+5d | 764 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
764 | Comm | Mktg | Eng | A |  | Graphic Options Approval in Epadex (DCIC) | 2d | Tue 6/20/28 | Thu 6/22/28 | 763 | 767768 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
766 | Comm | Artwork | AW |  |  | Claim approval # needed (link to POC work) | 3d | Mon 5/8/28 | Thu 5/11/28 | 702 |  | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
767 | Comm | Artwork | AW |  |  | Color development (assume 20 unique designs) | 20d | Thu 6/22/28 | Thu 7/20/28 | 764 | 769 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
768 | Comm | Mktg | Eng |  |  | Master Copy Meeting- w/Legal - legal number for master copy | 5d | Thu 6/22/28 | Thu 6/29/28 | 764 | 769 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
769 | Comm | Mktg | Eng |  |  | Master Copy approval - all waves (MF mtg) | 2d | Thu 7/20/28 | Mon 7/24/28 | 767768 | 770SS | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
770 | Comm | Mktg | Eng |  |  | Upload Master Copy | 2d | Thu 7/20/28 | Mon 7/24/28 | 769SS | 771 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
771 | Comm | Artwork | AW |  |  | Wave 2 | 3w | Mon 7/24/28 | Mon 8/14/28 | 770 | 772SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
772 | Comm | Artwork | AW |  |  | Wave 3 | 3w | Thu 7/27/28 | Thu 8/17/28 | 771SS+3d | 773SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
773 | Comm | Artwork | AW |  |  | Wave 4 | 3w | Tue 8/1/28 | Tue 8/22/28 | 772SS+3d | 774SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
774 | Comm | Artwork | AW |  |  | Wave 5 | 3w | Fri 8/4/28 | Fri 8/25/28 | 773SS+3d | 775SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
775 | Comm | Artwork | AW |  |  | Wave 6 | 3w | Wed 8/9/28 | Wed 8/30/28 | 774SS+3d | 776SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
776 | Comm | Artwork | AW |  |  | Wave 7 | 3w | Mon 8/14/28 | Mon 9/4/28 | 775SS+3d | 777SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
777 | Comm | Artwork | AW |  |  | Wave 8 | 3w | Thu 8/17/28 | Thu 9/7/28 | 776SS+3d | 778SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
778 | Comm | Artwork | AW |  |  | Wave 9 | 3w | Tue 8/22/28 | Tue 9/12/28 | 777SS+3d | 779SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
779 | Comm | Artwork | AW |  |  | Wave 10 | 3w | Fri 8/25/28 | Fri 9/15/28 | 778SS+3d | 780SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
780 | Comm | Artwork | AW |  |  | Wave 11 | 3w | Wed 8/30/28 | Wed 9/20/28 | 779SS+3d | 781SS+3d,805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
781 | Comm | Artwork | AW |  |  | Wave 12 | 3w | Mon 9/4/28 | Mon 9/25/28 | 780SS+3d | 960805 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Artwork |  | CR: AW
784 | Tech | TRO | Eng |  |  | Prepare TRA | 2w | Thu 1/23/31 | Thu 2/6/31 | 7FS-3mo | 8FS-3mo | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
785 | Tech | TRO | Eng |  |  | GTRO Updated (Risks summary, Learning plan & dashboard) | 2w | Fri 3/14/31 | Fri 3/28/31 | 7FS-6w |  | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
786 | Tech | Process | Process |  |  | Prepare TT&T plans | 1mo | Fri 3/14/31 | Tue 4/15/31 | 7FS-6w |  | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
787 | Tech | Pkg Dev | MPD |  |  | IP strategy complete | 0d | Thu 1/23/31 | Thu 1/23/31 | 7FS-3mo |  | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
788 | Tech | Pkg Dev | MPD |  |  | Patent & TM issues resolved | 0d | Thu 1/23/31 | Thu 1/23/31 | 7FS-3mo | 8FS-3mo | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
789 | Tech | PD | PD |  |  | POC template complete & approved | 0d | Tue 11/16/27 | Tue 11/16/27 | 607 | 701 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
790 | Tech | TRO | Process |  |  | Regulatory issues resolved | 0d | Thu 1/23/31 | Thu 1/23/31 | 7FS-3mo | 1068,8FS-3mo | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
791 | Supply | SNO | IOL |  |  | Agreement to Supply Network design | 0d | Fri 8/18/28 | Fri 8/18/28 | 643876870 |  | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
792 | Tech | Eng | Eng |  |  | TFS, PFS & Controls strategy final | 8mo | Tue 3/21/28 | Tue 11/21/28 | 574576 | 944 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
793 | Tech | Eng | Eng |  |  | Finalize layouts/models/flow sheets | 1w | Fri 1/7/28 | Thu 1/13/28 | 580 | 944 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
794 | Tech | Eng | Eng |  |  | CBDR #3 | 1d | Thu 3/23/28 | Fri 3/24/28 | 580,849SS | 796 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
795 | Tech | Eng | Eng |  |  | ISU RA #3 | 1d | Tue 3/21/28 | Tue 3/21/28 | 577 | 944 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
796 | Tech | Eng | Eng |  |  | CBDR #4 | 1d | Thu 9/7/28 | Fri 9/8/28 | 794979 | 944 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | LA: Technical Readiness
798 | Tech | Process | Process |  |  | Generate Final formula cards/Primary specs | 30d | Fri 8/18/28 | Thu 9/28/28 | 8.256e+23 | 1068SS,833 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | TR: Specs-Stds
799 | Tech | Process | Process |  |  | Reblend Stds - if applicable | 3mo | Fri 8/18/28 | Fri 11/17/28 | 821 | 833,804SS+1mo | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | TR: Specs-Stds
800 | Tech | Process | Process |  |  | ASL/RMS/RMPI | 3mo | Fri 8/18/28 | Fri 11/17/28 | 821917 | 831832 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | TR: Specs-Stds
801 | Tech | Process | Process |  |  | Process Control Standards | 2mo | Fri 8/18/28 | Wed 10/18/28 | 821 | 831 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | TR: Specs-Stds
802 | Tech | Process | Process |  |  | Mfg Stds (HDL Deviation Sheets) | 3mo | Fri 4/14/28 | Fri 7/14/28 | 817 | 798917833 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | All |  | TR: Specs-Stds
804 | Tech | Pkg Dev | MPD |  |  | Formula Cards S&S | 2.3mo | Tue 9/19/28 | Tue 11/28/28 | 799SS+1mo | 807878 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Pkg Stds
805 | Tech | Pkg Dev | MPD |  |  | Primary Pack S&S (caps, wraps, labels, transitions, corrugate, etc) | 2mo | Mon 9/25/28 | Fri 11/24/28 | 6.2863e+44 | 807878806 | Package | Qualify & Ready |  | Technical | Package |  | TR: Pkg Stds
806 | Tech | Pkg Dev | MPD |  |  | Other (tie sheets, corner posts, bulk shipper) S&S | 2w | Fri 11/24/28 | Fri 12/8/28 | 805 | 807878 | Formula, Package | Qualify & Ready |  | Technical | Formula, Package |  | TR: Pkg Stds
807 | Tech | Process | Process |  |  | WPPI | 2mo | Fri 12/8/28 | Thu 2/8/29 | 822804805806 | 1079 | Formula, Package, Eng Scope | Qualify & Ready |  | Technical | Formula, Package, Eng Scope |  | TR: Specs-Stds
808 | Tech | Process | Process |  |  | Product QEC | 2w | Thu 5/4/28 | Thu 5/18/28 | 701817 | 830 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Specs-Stds
809 | Tech | Pkg Dev | Vanessa |  |  | Packing QEC | 2w | Tue 8/25/26 | Mon 9/7/26 | 575 | 830 | Package | Qualify & Ready |  | Technical | Package |  | TR: Specs-Stds
810 | Tech | Process | Process |  |  | TFS | 2w | Fri 4/14/28 | Thu 4/27/28 | 817 | 830 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Specs-Stds
813 | Tech | Process | Process |  |  | Pilot Scale trials | 16w | Fri 12/17/27 | Thu 4/6/28 | 467473529634 | 815 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
814 | Tech | Process | Process | A |  | Planning and Approvals for Manufacturing Feasibility EO (Intermediates & FP) | 18d | Fri 4/7/28 | Tue 5/2/28 |  |  | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
815 | Tech | Process | Process |  |  | Develop and Approve initial Plan for EOs (Cost, Timing, etc) | 3d | Fri 4/7/28 | Tue 4/11/28 | 813593594595457 | 816,817SS | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
816 | Tech | Process | Process |  |  | Procure Raw Materials for inputs to formula (perfumes, etc) | 3w | Wed 4/12/28 | Tue 5/2/28 | 815 |  | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
817 | Tech | Process | Process |  |  | Manufacturing Feasibility EO (list all EOs and location) | 1w | Fri 4/7/28 | Thu 4/13/28 | 815SS | 8.2082e+26 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
818 | Tech | Process | Process |  |  | Basis for Scale Up | 0d | Thu 4/13/28 | Thu 4/13/28 | 4.6747e+17 |  | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
819 | Tech | Process | Process |  |  | Scale Up Stability - Physical | 130d | Thu 4/13/28 | Thu 10/12/28 |  |  | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
820 | Tech | Process | Process |  |  | 6wk read | 42ed | Thu 4/13/28 | Thu 5/25/28 | 817 | 821 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
821 | Tech | Process | Process |  |  | 12 wk read | 84ed | Thu 5/25/28 | Thu 8/17/28 | 817820 | 798801799800 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
822 | Tech | Process | Process |  |  | 26 wk read | 182ed | Thu 4/13/28 | Thu 10/12/28 | 817 | 944807 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
823 | Tech | Process | Process |  |  | Stability suds | 90ed | Thu 4/13/28 | Wed 7/12/28 | 817 | 798 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
824 | Tech | Process | Process |  |  | Chemical Risk Assessment on All Products | 1w | Tue 3/14/28 | Mon 3/20/28 | 603597 | 798 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
825 | Tech | Process | Process |  |  | MST Report | 2w | Fri 4/14/28 | Thu 4/27/28 | 817 | 1068798 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Product Ready
826 | Tech | Process | Process |  |  | Product/Making CQV | 206.5d | Thu 3/9/28 | Fri 12/22/28 |  |  | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
827 | Tech | Plant | Tad |  |  | Determine what to make and how much for CQ | 3w | Thu 3/9/28 | Thu 3/30/28 | 5 | 830829 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
828 | Tech | Process | Process |  |  | Confirm when materials on site | 0d | Fri 10/6/28 | Fri 10/6/28 | 838842917 | 833 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
829 | Tech | SNO | IOL |  |  | Confirm Downtime for CQ in SAP | 1w | Thu 3/30/28 | Thu 4/6/28 | 827 | 830 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
830 | Tech | Process | Process |  |  | Complete PQ Document | 2mo | Thu 5/18/28 | Wed 7/19/28 | 827808810829809 | 831,833,8 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
831 | Tech | Plant | Tad |  |  | IQ/OQ Raw Materials | 2w | Mon 11/20/28 | Fri 12/1/28 | 830800801 | 833,8 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
832 | Tech | Process | Process |  |  | Stds (Odor/Appearance) | 2w | Mon 11/20/28 | Fri 12/1/28 | 800 | 833944 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
833 | Tech | Process | Process |  |  | Complete Product CQV | 3w | Mon 12/4/28 | Fri 12/22/28 | 8.3283e+20 | 1079 | Formula | Qualify & Ready |  | Technical | Formula |  | TR: Prod R: CQV
836 | Tech | Eng | Eng |  |  | Order/Receive equipment (tanks, agitators, valves, etc) | 13w | Wed 12/1/27 | Wed 3/1/28 | 40 | 576SS,837 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
837 | Tech | Eng | Eng |  |  | Construction | 5mo | Wed 3/1/28 | Wed 8/2/28 | 836 | 838 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
838 | Tech | Eng | Eng |  |  | CQ (eng) | 6w | Wed 8/2/28 | Wed 9/13/28 | 837 | 828,8 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
840 | Tech | Eng | Robert |  |  | Other/Receive Formula equipment | 13w | Thu 3/9/28 | Thu 6/8/28 | 5 | 841 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
841 | Tech | Eng | Robert |  |  | Construction | 3mo | Thu 6/8/28 | Fri 9/8/28 | 840 | 842 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
842 | Tech | Eng | Robert |  |  | CQ (eng) | 4w | Fri 9/8/28 | Fri 10/6/28 | 841 | 828,8 | Formula, Eng Scope | Qualify & Ready |  | Technical | Formula, Eng Scope |  | TR: Process Ready
844 | Tech | Pkg Dev | MPD |  |  | Handover process to MPO approved | 1w | Tue 12/24/30 | Tue 12/31/30 | 7FS-4mo | 8FS-4mo | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Package Ready
846 | Tech | Eng | Eng |  |  | 60% Design Basis Mechanical Development | 1w | Fri 12/10/27 | Thu 12/16/27 | 633639 | 847SS+2w,634FF,848 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
847 | Tech | Eng | Eng |  |  | 60% Design Basis Electrical Development | 1w | Fri 12/24/27 | Thu 12/30/27 | 846SS+2w,639 | 578,579,580SS | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
848 | Tech | Eng | Eng |  |  | 50% EI Development - Mechanical & Sign-off | 5w | Thu 3/9/28 | Thu 4/13/28 | 5639846 | 849SS+2w,855 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
849 | Tech | Eng | Eng |  |  | 50% EI Development - Electric & Sign-off | 5w | Thu 3/23/28 | Thu 4/27/28 | 848SS+2w | 851,794SS | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
850 | Tech | Eng | Eng |  |  | Order Long Lead Time Packing (Laser, Vision, Cap Delivery) | 12w | Thu 3/9/28 | Thu 6/1/28 | 5 | 856 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
851 | Tech | Eng | Eng |  |  | EI “Equipment Sourcing” Ready | 0d | Thu 4/27/28 | Thu 4/27/28 | 5849 | 852 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
852 | Tech | Eng | Eng |  |  | Lead Lines EI Mechanical Development & IFC | 6w | Thu 4/27/28 | Thu 6/8/28 | 851 | 853SS+2w,856 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
853 | Tech | Eng | Eng |  |  | Lead Lines EI Electrical Development & IFC | 6w | Thu 5/11/28 | Thu 6/22/28 | 852SS+2w | 856 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Packing Ready
855 | Tech | Eng | Eng |  |  | Lead Lines Equipment Sourcing for Plants | 6w | Thu 4/13/28 | Thu 5/25/28 | 5848 | 856 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Pack R: CQV
856 | Tech | Eng | Eng |  |  | Lead Lines Equipment on Site | 0d | Thu 6/22/28 | Thu 6/22/28 | 855852853850 | 859857 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Pack R: CQV
857 | Tech | Eng | Eng |  |  | Construction Planning | 3w | Thu 6/22/28 | Thu 7/13/28 | 856 | 858FS+4w | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Pack R: CQV
858 | Tech | Eng | Eng |  |  | Lead Lines Equipment Installation | 15d | Thu 8/10/28 | Thu 8/31/28 | 857FS+4w | 859 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Pack R: CQV
859 | Tech | Eng | Eng |  |  | CQV Lead Lines for different variants | 8w | Thu 8/31/28 | Thu 10/26/28 | 856858 | 978SS-6w,1069,944,1075 | Package, Eng Scope | Qualify & Ready |  | Technical | Package, Eng Scope |  | TR: Pack R: CQV
865 | Supply | SNO | Perfume |  |  | Initial by Variant/Size Volume Forecast from Demand/Finance | 5d | Wed 6/28/28 | Wed 7/5/28 | 5FS+3.6mo | 868 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | SC Read: Inv Build: 7030 Plan
866 | Supply | SNO | MLL/MIL |  |  | Update Merchandising/Customization Assumptions | 10d | Wed 6/28/28 | Wed 7/12/28 | 5FS+3.6mo | 868 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | SC Read: Inv Build: 7030 Plan
867 | Supply | SNO | MLL/MIL |  |  | Update to Shelf Transition Plans | 10d | Wed 6/28/28 | Wed 7/12/28 | 5FS+3.6mo | 868 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | SC Read: Inv Build: 7030 Plan
868 | Supply | SNO | Taylor |  |  | Update RCCP with build plugs | 9d | Wed 7/12/28 | Tue 7/25/28 | 865866867 | 870869 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical Scope | Package, Formula, Eng Scope |  | SC Read: Inv Build: 7030 Plan
869 | Supply | SNO | Perfume | A |  | Approval of 70/30 Plan | 2d | Tue 7/25/28 | Thu 7/27/28 | 868 | 894921922896 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical Scope | Package, Formula, Eng Scope |  | SC Read: Inv Build: 7030 Plan
870 | Supply | SNO | Lori |  |  | C:D checks and build plans with Major Suppliers | 12d | Tue 7/25/28 | Thu 8/10/28 | 868 | 791 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical Scope | Package, Formula, Eng Scope |  | SC Read: Inv Build: 7030 Plan
872 | Supply | SNO | Perfume |  |  | Initial by Variant/Size Volume Forecast from Demand/Finance | 5d | Wed 10/7/26 | Tue 10/13/26 | 861 | 875 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Inv Build: 8020 plan
873 | Supply | CMS | Andrew |  |  | Update Merchandising/Customization Assumptions | 2d | Wed 10/7/26 | Thu 10/8/26 | 861 | 875 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Inv Build: 8020 plan
874 | Supply | SNO | MLL/MIL |  |  | Update to Shelf Transition Plans | 2d | Wed 10/7/26 | Thu 10/8/26 | 861 | 875 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Inv Build: 8020 plan
875 | Supply | SNO | Taylor |  |  | Update RCCP with build plugs | 7d | Wed 10/14/26 | Thu 10/22/26 | 872873874 | 876895898 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Inv Build: 8020 plan
876 | Supply | SNO | Perfume | A |  | Approval of 80/20 Plan | 2d | Wed 8/16/28 | Fri 8/18/28 | 875910 | 900903791944 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Inv Build: 8020 plan
878 | Supply | SNO | IOL |  |  | IOPT MD input RPMI | 14d | Fri 12/8/28 | Thu 12/28/28 | 804805806 | 879,880FS-2w | Package, Formula, Eng Scope | Qualify & Ready |  | Technical | Package, Formula, Eng Scope |  | SC Read: MD
879 | Supply | SNO | Taylor |  |  | Costing RPMI at supplier and SA/PO set up in PUMA | 7d | Thu 12/28/28 | Mon 1/8/29 | 878 | 882 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical | Package, Formula, Eng Scope |  | SC Read: MD
880 | Supply | SNO | Taylor |  |  | Obtain costing resources | 23d | Thu 12/14/28 | Tue 1/16/29 | 878FS-2w | 881FF | Package, Formula, Eng Scope | Qualify & Ready |  | Technical | Package, Formula, Eng Scope |  | SC Read: MD
881 | Supply | SNO | Taylor |  |  | Complete master data on new brandcodes | 5d | Tue 1/9/29 | Tue 1/16/29 | 880FF | 887 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical | Package, Formula, Eng Scope |  | SC Read: MD
882 | Supply | SNO | Taylor |  |  | FP brandcode costed (master data complete) | 3d | Mon 1/8/29 | Thu 1/11/29 | 879 | 889 | Package, Formula, Eng Scope | Qualify & Ready |  | Technical | Package, Formula, Eng Scope |  | SC Read: MD
885 | Supply | SNO | Joe S |  |  | GDF (Global Demand Forecast) Setup | 3w | Wed 6/28/28 | Wed 7/19/28 | 5FS+3.6mo | 886 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
886 | Supply | SNO | Joe S |  |  | Validate new and old SKU's in GDF/Forecast Template | 2w | Wed 7/19/28 | Wed 8/2/28 | 885 | 887 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
887 | Supply | SNO | Joe |  |  | Test volume data flow after master data set up | 2d | Tue 1/16/29 | Thu 1/18/29 | 881886 | 889 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
889 | Supply | SNO | Joe |  |  | Demand passes prelim BOP (date needed) | 2d | Thu 1/18/29 | Mon 1/22/29 | 882887 | 890 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
890 | Supply | SNO | Joe |  |  | Open producttion versions | 1d | Mon 1/22/29 | Tue 1/23/29 | 889 | 891 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
891 | Supply | SNO | Joe |  |  | Demand passes final BOP (date needed) | 4d | Tue 1/23/29 | Mon 1/29/29 | 890 | 810231059 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: BOP
894 | Supply | SNO | Joel |  |  | Request the 70/30 Probability Bundle Split | 2d | Thu 7/27/28 | Mon 7/31/28 | 869 | 9.0591e+17 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Space
895 | Supply | SNO | Joel |  |  | Request the 80/20 Probablility Bundle Split | 2d | Fri 10/23/26 | Mon 10/26/26 | 875 | 914910 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Space
896 | Supply | SNO | Joel |  |  | Inventory Space for Current/Other | 2d | Thu 7/27/28 | Mon 7/31/28 | 869 | 914 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Space
897 | Supply | SNO | Joel |  |  | Any relevant ATS for ship/store/stack | 1mo | Wed 6/28/28 | Fri 7/28/28 | 5FS+3.6mo | 914 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Space
898 | Supply | SNO | Joel |  |  | Confrim Supplier Space for build | 2d | Fri 10/23/26 | Mon 10/26/26 | 875 | 914 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Space
900 | Supply | SNO | Joel |  |  | Intial Carrier capacity assessment for launch | 1d | Fri 8/18/28 | Mon 8/21/28 | 876 | 914 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Carrier
901 | Supply | SNO | Joel |  |  | Locked carrier capacity (production schedule out (DATE) and customer pull pattern) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  | 902 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Carrier
902 | Supply | SNO | Joel |  |  | PrePurchase Capacity (when do you need this? - physical distribution) - note when to lock | 8w | Tue 11/4/25 | Tue 12/30/25 | 901 | 8931 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Carrier
903 | Supply | SNO | Joel |  |  | Evaluate need for additional drop lot space at ship points | 1d? | Fri 8/18/28 | Mon 8/21/28 | 876 | 914931 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Carrier
905 | Supply | SNO | Joel |  |  | Explore warehouse locations (options analysis) | 10d | Mon 7/31/28 | Mon 8/14/28 | 894 | 910 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
906 | Supply | SNO | Joel |  |  | Determine if need double stacking for any other part of the bundle | 10d | Mon 7/31/28 | Mon 8/14/28 | 894 | 910 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
907 | Supply | SNO | Joel |  |  | Determine if new warehouse should it be a ship point (opportunistic shipment not SVGroup) | 10d | Mon 7/31/28 | Mon 8/14/28 | 894 | 910912 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
908 | Supply | SNO | Joel |  |  | Determine if it makes sense to shift any IRI districts for launch (cost impacts due to GM - analyis for category | 10d | Mon 7/31/28 | Mon 8/14/28 | 894 | 910 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
909 | Supply | SNO | Joel |  |  | Strategy for freeing up enough space at the ship points to get right mix for launch | 10d | Mon 7/31/28 | Mon 8/14/28 | 894 | 910 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
910 | Supply | SNO | Joel |  |  | Finalize Storage Strategy with 80/20 Confidence | 2d | Mon 8/14/28 | Wed 8/16/28 | 8.9591e+17 | 8.761e+28 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Storage Strat
912 | Supply | SNO | Joel |  |  | Physical distribution for new ship point (if needed) | 0d | Mon 8/14/28 | Mon 8/14/28 | 907 | 9141016 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Transportation
913 | Supply | SNO | Joel |  |  | DSD options (what business to ship/ not normal lane and need to get capacity/paper - are we even doing this | 0d | Fri 5/30/31 | Fri 5/30/31 | 24,26,180 | 1016 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Transportation
914 | Supply | SNO | Joel |  |  | Total Costs & Timing Update for Space (to incl interfreight, etc) | 3d | Mon 8/21/28 | Thu 8/24/28 | 8.949e+23 | 915 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Costs
915 | Supply | SNO | Joel |  |  | Approval for Additional Space (MO Ldr) | 5d | Thu 8/24/28 | Thu 8/31/28 | 914 | 8 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Package, Formula |  | SC Read: Costs
917 | Supply | MSM | Ria |  |  | New Material Qualification | 1w | Mon 7/17/28 | Fri 7/21/28 | 802 | 800828944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
918 | Supply | SNO | IOL |  |  | Global Mat'l Supply Logistics plan | 3mo | Tue 3/21/28 | Tue 6/20/28 | 642 | 944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
919 | Supply | SNO | Jessica |  |  | Packing Materials supplier assessment | 5mo | Tue 3/21/28 | Mon 8/21/28 | 642 | 944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
920 | Supply | SNO | Gene |  |  | Raw Materials supplier assessment | 3mo | Tue 3/21/28 | Tue 6/20/28 | 642 | 944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
921 | Supply | SNO | IOL |  |  | Material supply vs. demand | 2w | Thu 7/27/28 | Thu 8/10/28 | 644869 | 944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
922 | Supply | SNO | MSM TBD |  |  | Supplier base capability/reliability - High Level Analysis | 4w | Thu 7/27/28 | Thu 8/24/28 | 644869 | 944 | Formula, Package | Qualify & Ready |  | Technical Scope | Package, Formula |  | SC Read: Matl Qual
926 | Comm | A&I | A&I | A |  | Detailed Forecast (SIMPL red sheet) | 0d | Thu 8/10/28 | Thu 8/10/28 | 5FS+5mo | 935936937938 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Volume
927 | Comm | A&I | A&I |  |  | Awareness, Trial / Penetration | 0d | Thu 8/10/28 | Thu 8/10/28 | 5FS+5mo | 935936937938 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | LA Financials: Volume
928 | Comm | A&I | A&I |  |  | Cannibalization | 0d | Thu 8/10/28 | Thu 8/10/28 | 5FS+5mo | 935936937938 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | LA Financials: Volume
929 | Comm | A&I | A&I | A |  | Source of Volume Analysis | 0d | Thu 8/10/28 | Thu 8/10/28 | 5FS+5mo | 935936937938 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | LA Financials: Volume
931 | Supply | SNO | Kelvin |  |  | Transition Costs Complete | 1w | Mon 8/21/28 | Mon 8/28/28 | 662,5FS+5mo,902,903,910 | 942935936937938 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Cost
932 | Comm | Finance | Jenny |  |  | Capital Spend complete | 1w | Thu 8/10/28 | Thu 8/17/28 | 661,5FS+5mo | 942935936937938 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Cost
933 | Comm | Finance | Jenny |  |  | Formula cost complete | 1w | Thu 8/10/28 | Thu 8/17/28 | 663,5FS+5mo | 942935936937938 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Cost
935 | Comm | Finance | Finance | A |  | SIMPL Financial Fact Sheet | 1w | Mon 8/28/28 | Mon 9/4/28 | 9.2693e+20 | 939 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
936 | Comm | Finance | Finance | A |  | Gross and Incremental NOS, DOPAT | 1w | Mon 8/28/28 | Mon 9/4/28 | 9.2693e+20 | 939 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
937 | Comm | Finance | Finance | A |  | Gross Margin | 1w | Mon 8/28/28 | Mon 9/4/28 | 9.2693e+20 | 939 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
938 | Comm | Finance | Finance | A |  | NPV | 1w | Mon 8/28/28 | Mon 9/4/28 | 9.2693e+20 | 939 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
939 | Comm | Finance | Finance | A |  | Business model & pricing | 1w | Mon 9/4/28 | Mon 9/11/28 | 935936937938 | 942 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
940 | Comm | Finance | Finance |  |  | Distribution Inputs | 1w | Fri 7/7/28 | Fri 7/14/28 | 673 | 941 | Commercial Facing | Qualify & Ready |  | Commercial Facing | Mandatory |  | LA Financials: Assump
941 | Comm | Finance | Finance |  |  | Volume Analysis | 8w | Fri 7/14/28 | Fri 9/8/28 | 940 | 942 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
942 | Comm | Finance | Finance |  |  | Update Financial Analysis for LPA-LA | 1w | Mon 9/11/28 | Mon 9/18/28 | 941933932931939 | 945 | All | Qualify & Ready |  | All | Mandatory |  | LA Financials: Assump
949 | [5 empty] | Anthem approved | 1d? | Fri 6/30/28 | Mon 7/3/28 | 713722 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
950 | [5 empty] | USH Approved | 1d? | Fri 6/30/28 | Mon 7/3/28 | 713722 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
951 | [5 empty] | Copy Testing results | 1d? | Fri 6/30/28 | Mon 7/3/28 | 713722 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
952 | Comm | Mktg | Mktg |  |  | Print Execution | 6mo | Thu 6/8/28 | Mon 12/11/28 | 724 | 1081 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
953 | Comm | Mktg | Mktg |  |  | Digital Execution | 44d | Mon 7/17/28 | Fri 9/15/28 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
954 | Comm | Mktg | Mktg |  |  | Digital Execution | 2w | Mon 7/17/28 | Mon 7/31/28 | 729 | 1081 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
955 | Comm | Mktg | Mktg |  |  | Search Execution | 2mo | Mon 7/17/28 | Fri 9/15/28 | 729 | 1081 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
956 | Comm | Mktg | Mktg |  |  | iMedia Execution | 2mo | Mon 7/17/28 | Fri 9/15/28 | 729 | 1081 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
957 | Comm | Mktg | Mktg |  |  | In Store Execution | 66d | Tue 6/20/28 | Wed 9/20/28 | 733 | 1081 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Mandatory |  | Del: Mkt Plan Exec
959 | Supply | SNO | IOL |  |  | PDR 1 (XX Item) Print Tools - date needed | 20d | Mon 7/3/28 | Mon 7/31/28 | 761 | 9608051075 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Artwork |  | Del: Mkt Plan Exec
960 | Supply | SNO | IOL |  |  | PDR 2 (YY Item) Print Tools - date needed | 15d | Mon 9/25/28 | Mon 10/16/28 | 959781 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Artwork |  | Del: Mkt Plan Exec
962 | Supply | CMS | Marciniak |  |  | C&F Submitted | 1d? | Thu 3/2/28 | Fri 3/3/28 | 6 | 963 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
963 | Supply | CMS | Marciniak |  |  | Design Frozen | 0d | Fri 3/3/28 | Fri 3/3/28 | 962 | 964 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
964 | Supply | CMS | Marciniak |  |  | Case Weights & Measures (CW&M) attached to C&F | 2d | Fri 3/3/28 | Tue 3/7/28 | 963 | 965 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
965 | Supply | CMS | Marciniak |  |  | C&F Final | 12d | Tue 3/7/28 | Thu 3/23/28 | 964 | 966 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
966 | Supply | CMS | Marciniak |  |  | PDR submitted into ePadex | 1d | Thu 3/23/28 | Fri 3/24/28 | 965 | 967 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
967 | Supply | CMS | Marciniak |  |  | GBP Release | 14d | Fri 3/24/28 | Thu 4/13/28 | 966 | 968 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
968 | Supply | CMS | Marciniak |  |  | Demand Flowing | 2d | Thu 4/13/28 | Mon 4/17/28 | 967 | 969 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
969 | Supply | CMS | Marciniak |  |  | Art Files Released to CM | 51d | Mon 4/17/28 | Tue 6/27/28 | 968 | 970 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
970 | Supply | CMS | Marciniak |  |  | Manual Approved | 1d | Tue 6/27/28 | Wed 6/28/28 | 969 | 971 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
971 | Supply | CMS | Marciniak |  |  | CRWS Approved | 1d | Wed 6/28/28 | Thu 6/29/28 | 970 | 972 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
972 | Supply | CMS | Marciniak |  |  | PR Approved | 6d | Thu 6/29/28 | Fri 7/7/28 | 971 | 973 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
973 | Supply | CMS | Marciniak |  |  | Feeder Stock (Product Packaged into currogate displays) | 34d | Fri 7/7/28 | Thu 8/24/28 | 972 | 974 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
974 | Supply | CMS | IOL |  |  | Customization Product at Location to build displays | 1d | Thu 8/24/28 | Fri 8/25/28 | 973 | 975 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
975 | Supply | SNO | Perfume |  |  | C:D Analysis of High side demand | 1mo | Fri 8/25/28 | Tue 3/25/31 | 678974 | 945976 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
976 | Supply | SNO | Perfume |  |  | Conversion remnant plan approved | 1mo | Tue 3/25/31 | Thu 4/24/31 | 678975 | 945 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Package, Formula |  | Del: Customization
978 | Tech | Eng | Eng |  |  | EI Mechanical 90% Development & IFC | 5w | Thu 7/20/28 | Thu 8/24/28 | 859SS-6w | 979SS+2w,980FS-1w | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
979 | Tech | Eng | Eng |  |  | EI Electrical 90% Development & IFC | 5w | Thu 8/3/28 | Thu 9/7/28 | 978SS+2w | 796,981FS-1w | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
980 | Tech | Eng | Eng |  |  | Remaining Line Equipment Mech Sourcing Line (remaining lines) | 3w | Thu 8/17/28 | Thu 9/7/28 | 978FS-1w | 982 | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
981 | Tech | Eng | Eng |  |  | Remaining Line Equipment Elec Sourcing Line (remaining Lines) | 3w | Thu 8/31/28 | Thu 9/21/28 | 979FS-1w | 983 | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
982 | Tech | Eng | Eng |  |  | Remaining Line Equipment Mech Purchase (remaining lines) | 6w | Thu 9/7/28 | Thu 10/19/28 | 980 | 985987 | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
983 | Tech | Eng | Eng |  |  | Remaining Line Equipment Elec Purchase (remaining lines) | 6w | Thu 9/21/28 | Thu 11/2/28 | 981 | 985987 | Eng Scope, New Package | Launch |  | Technical Scope | Eng Scope, New Package |  | Del: Pkg Delivery
985 | Tech | Eng | Eng |  |  | Construction Planning on line A | 2w | Thu 11/2/28 | Thu 11/16/28 | 982983 | 986 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
986 | Tech | Eng | Eng |  |  | Line A Construction | 2d | Thu 11/16/28 | Mon 11/20/28 | 985 | 992 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
987 | Tech | Eng | Eng |  |  | Construction Planning line B | 2w | Thu 12/7/28 | Thu 12/21/28 | 982983992 | 988 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
988 | Tech | Eng | Eng |  |  | Line B Construction | 2d | Thu 12/21/28 | Mon 12/25/28 | 987 | 993 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
989 | Tech | Eng | Eng |  |  | Construction Planning C | 2w | Wed 12/27/28 | Wed 1/10/29 | 993FS-10d | 990 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
990 | Tech | Eng | Eng |  |  | Line C Construction | 2d | Wed 1/10/29 | Fri 1/12/29 | 989 | 994 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: Post Release Constr
992 | Tech | Eng | Eng |  |  | Line A - CQV (Dates and Variants) | 13d | Mon 11/20/28 | Thu 12/7/28 | 986 | 9871077 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
993 | Tech | Eng | Eng |  |  | Line B - CQV (Dates and Variants) | 12d | Mon 12/25/28 | Wed 1/10/29 | 988 | 989FS-10d,1077 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
994 | Tech | Eng | Eng |  |  | Line C - CQV (Dates and Variants) | 13d | Fri 1/12/29 | Wed 1/31/29 | 990 | 995SS,996FS+10d,1077 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
995 | Tech | Eng | Eng |  |  | Remaining 2 Formulas/Packages (list variants here) | 3w | Fri 1/12/29 | Fri 2/2/29 | 994SS |  | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
996 | Tech | Eng | Eng |  |  | Line D CQV - assumed part of inventory build | 3d | Wed 2/14/29 | Mon 2/19/29 | 994FS+10d | 997 | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
997 | Tech | Eng | Eng |  |  | Line E CQV - assumed part of inventory build | 1d | Mon 2/19/29 | Tue 2/20/29 | 996 |  | Eng Scope | Launch |  | Technical Scope | Eng Scope |  | Del: CQV
999 | Tech | PR | PR |  |  | Order Label/Artwork Materials | 2w | Thu 9/24/26 | Wed 10/7/26 | 169 | 10001001 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1000 | Tech | PR | PR |  |  | Primary Pack Production | 1w | Thu 10/8/26 | Wed 10/14/26 | 999 | 1003 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1001 | Tech | PR | PR |  |  | Label Production | 1w | Thu 10/8/26 | Wed 10/14/26 | 999 | 1003 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1002 | Tech | PR | PR |  |  | Sales Sample Primary Pack Delivery to Sampling Solutions | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 1003 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1003 | Tech | PR | PR |  |  | Sales Sample Assembly at Sampling Solutions | 1w | Thu 10/15/26 | Wed 10/21/26 | 100010011002 | 1004 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1004 | Tech | PR | PR |  |  | Agency Sales Samples Delivery | 11d | Thu 10/22/26 | Tue 11/10/26 | 1003 | 18,19,20 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Sales Samples
1007 | Execution | IOL | IOL |  |  | Shipment deployment Need internal or external to the PSC | 1d? | Tue 5/27/31 | Wed 5/28/31 | 7FS+1mo |  | All | Launch |  | All | Package, Product |  | Del: Prod Oper Strat
1010 | Execution | IOL | IOL |  |  | Write COP (link to ready to invest) | 1w | Mon 11/3/25 | Fri 11/7/25 |  | 1011 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse Space
1011 | Execution | IOL | IOL |  |  | Write exploratory ROA | 1w | Mon 11/10/25 | Fri 11/14/25 | 1010 | 1012 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse Space
1012 | Execution | IOL | IOL |  |  | MO Leader concurrence | 1w | Mon 11/17/25 | Fri 11/21/25 | 1011 | 1013 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse Space
1013 | Execution | IOL | IOL |  |  | Official ROA | 1w | Mon 11/24/25 | Mon 12/1/25 | 1012 | 10161014 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse Space
1014 | Execution | IOL | IOL |  |  | Warehouse Available | 0d | Mon 12/1/25 | Mon 12/1/25 | 1013 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse Space
1016 | Execution | IOL | IOL |  |  | T&W Readiness Kick-off (PSC, MDO, GBU) | 0d | Fri 5/30/31 | Fri 5/30/31 | 1013912913910 | 1.0171e+19 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1017 | Execution | IOL | IOL |  |  | Transportation purchases for new lanes | 1mo | Fri 5/30/31 | Tue 7/1/31 | 1016 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1018 | Execution | IOL | IOL |  |  | Transportation BCP - ice storms north & tornadoes in south | 1mo | Fri 5/30/31 | Tue 7/1/31 | 1016 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1019 | Execution | IOL | IOL |  |  | RTCIS/PRIME Set Up | 1mo | Fri 5/30/31 | Tue 7/1/31 | 1016 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1020 | Execution | IOL | IOL |  |  | 3PL set up to manage shuttles in and out of facility (if only storage facility) | 1mo | Fri 5/30/31 | Tue 7/1/31 | 1016 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1021 | Execution | IOL | IOL |  |  | Order guide changes and APAL | 1mo | Fri 5/30/31 | Tue 7/1/31 | 1016 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Whse/Transp Read
1023 | Execution | SNO | MLL/MIL |  |  | Develop Remnant Strategy | 1d? | Mon 1/29/29 | Tue 1/30/29 | 891 | 1024 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1024 | Execution | SNO | CSNP/BP |  |  | Fill vs scrap decision on reshippers initial evaluation | 1d? | Tue 1/30/29 | Wed 1/31/29 | 1023 | 1025 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1025 | Execution | SNO | CSNP/BP |  |  | Secondary market/remnant | 146d | Wed 1/31/29 | Thu 8/23/29 | 1024 | 1026 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1026 | Execution | SNO | CSNP/BP |  |  | Fill vs scrap decision on reshippers final look | 1d? | Thu 8/23/29 | Fri 8/24/29 | 1025 | 1027 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1027 | Execution | SNO | CSNP/BP |  |  | Execute scrap | 146d | Fri 8/24/29 | Mon 3/18/30 | 1026 | 1028 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1028 | Execution | SNO | CSNP/BP |  |  | Manage visibility of remnants - what we have left; consolidating them, etc | 1d? | Mon 3/18/30 | Tue 3/19/30 | 1027 | 1029 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1029 | Execution | SNO | CSNP/BP |  |  | Overall strategy of remnants (from MS&P) | 1d? | Tue 3/19/30 | Wed 3/20/30 | 1028 | 1030 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1030 | Execution | SNO | CSNP/BP |  |  | Is there any end date to move old product into market through NPI disposition | 1d? | Wed 3/20/30 | Thu 3/21/30 | 1029 | 1031 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1031 | Execution | Mktg | Mktg |  |  | FSCI Plans - Runout of Current / Merchandising Impact | 1d? | Thu 3/21/30 | Fri 3/22/30 | 1030 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Remnant Mgmt
1034 | Execution |  | Joe S |  |  | Acquire Access/License to manage | 1w | Wed 6/28/28 | Wed 7/5/28 | 5FS+3.6mo | 1035 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Managed Supply
1035 | Execution |  | Joe S |  |  | SODE file creation for bundle | 1d? | Wed 7/5/28 | Thu 7/6/28 | 1034 | 1036 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Managed Supply
1036 | Execution |  | Joe S |  |  | Develop GBP Materials for Managed Supply Guildelines | 1d? | Thu 7/6/28 | Fri 7/7/28 | 1035 | 1037 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Managed Supply
1037 | Execution |  | Perfume |  |  | Acquire systems support for managed supply report development | 1d? | Fri 7/7/28 | Mon 7/10/28 | 1036 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Managed Supply
1039 | Execution |  | Joe S |  |  | Develop team template | 1d? | Mon 11/3/25 | Mon 11/3/25 |  | 1040 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1040 | Execution |  | tbd - systems resource |  |  | Develop Spotfire reports | 1d? | Tue 11/4/25 | Tue 11/4/25 | 1039 | 1041 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1041 | Execution |  | Joe S |  |  | Populate team templates with run rates | 1d? | Wed 11/5/25 | Wed 11/5/25 | 1040 | 1042 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1042 | Execution |  | Joe S |  |  | Create a one pager for the teams for how to fill out template | 1d? | Thu 11/6/25 | Thu 11/6/25 | 1041 | 1043 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1043 | Execution |  | Joe S |  |  | Train teams on template | 1d? | Fri 11/7/25 | Fri 11/7/25 | 1042 | 1044 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1044 | Execution |  | Joe S |  |  | Validation of the overall tool and forecast template process | 1d? | Mon 11/10/25 | Mon 11/10/25 | 1043 | 1045 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1045 | Execution |  | Joe S |  |  | Templates sent out | 1d? | Tue 11/11/25 | Tue 11/11/25 | 1044 | 1046 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1046 | Execution |  | Joe S |  |  | Month 1 Forecast Proposal (date needed) | 1d? | Wed 11/12/25 | Wed 11/12/25 | 1045 | 1047 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1047 | Execution |  | Joe S |  |  | Month 2 Forecast Update (date needed) | 1d? | Thu 11/13/25 | Thu 11/13/25 | 1046 | 1048 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1048 | Execution |  | Joe S |  |  | Month 3 Forecast Lock (date needed) | 1d? | Fri 11/14/25 | Fri 11/14/25 | 1047 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: By Country Supply
1050 | Execution |  | MLL/MIL / Natalie |  |  | Understand SAP ordering systems capability for potential Forecast / Order Compliance Interventions; CSO - OMA Education Program | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1051 | Execution |  |  |  |  | PSC org up to speed | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1052 | Execution |  |  |  |  | Daily Processes | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1053 | Execution |  | MLL/MIL |  |  | First Delivery Orders Due (date due) | 1d? | Tue 3/4/31 | Wed 3/5/31 | 28FS-9w |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1054 | Execution |  |  |  |  | Last Order date for FDD (date here) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1055 | Execution |  | MLL/MIL |  |  | FDD Order Consolidation Date (date here) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1056 | Execution |  | MLL/MIL |  |  | Last Order Date for Current Product (date here) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1057 | Execution |  | MLL/MIL |  |  | Last Ship Date for other Current Product (date here) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Orders
1059 | Execution | SNO | SIP |  |  | Create builds via SAFTS in SAP | 1d? | Mon 1/29/29 | Tue 1/30/29 | 891 | 1060 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Cur Inv Build
1060 | Execution | SNO | SIP |  |  | Complete current inventory SAFTs at large suppliers (Lima) | 0d | Tue 1/30/29 | Tue 1/30/29 | 1059 | 1061 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Cur Inv Build
1061 | Execution | SNO | SIP |  |  | Complete FP SAFTs for current inventory | 61d | Tue 1/30/29 | Wed 4/25/29 | 1060 | 1062 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Cur Inv Build
1062 | Execution | SNO | SIP |  |  | Current Build SOP | 1d? | Tue 7/1/31 | Wed 7/2/31 | 1.0171e+23 |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Cur Inv Build
1064 | Execution | SNO | SIP |  |  | Complete Bundle builds at Large Suppliers | 0d | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: New Inv Build
1065 | Execution | SNO | SIP |  |  | Formulas aval (date needed) | 1d? | Mon 11/3/25 | Mon 11/3/25 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: New Inv Build
1066 | Execution | SNO | SIP |  |  | Complete FP SAFTs for new product (by plant) | 51d | Mon 11/3/25 | Tue 1/13/26 |  |  | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: New Inv Build
1068 | Execution | PR | PR |  |  | SMART | 4w | Thu 1/23/31 | Thu 2/20/31 | 790,825,798SS | 1070 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Prod/Inv Build
1069 | Execution | Eng | Eng |  |  | G2Target complete | 2mo | Thu 10/26/28 | Wed 12/27/28 | 859 | 1078 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Prod/Inv Build
1070 | Execution | TRO | TRL |  |  | Readiness Report | 3w | Thu 2/20/31 | Thu 3/13/31 | 1068 | 1078 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Prod/Inv Build
1072 | Execution | SNO | Lori |  |  | Totes | 2w | Wed 8/16/28 | Wed 8/30/28 | 910 | 1075 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Matl Supply
1073 | Execution | SNO | Lori |  |  | non SAP consumables (tiesheets, stretchwrap) | 2w | Wed 8/16/28 | Wed 8/30/28 | 910 | 1078 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Matl Supply
1074 | Execution | SNO | Lori |  |  | Pallets | 2w | Wed 8/16/28 | Wed 8/30/28 | 910 | 1078 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Matl Supply
1075 | Execution | SNO | Lori |  |  | SubAssembly - new parts (onsite and ready for use) | 40d | Thu 10/26/28 | Thu 12/21/28 | 9109591072859 | 1078 | Commercial Concept/Sell-in | Launch |  | Commercial Facing | Product, Package, Artwork |  | Del: Matl Supply
1077 | Execution | SNO | Tad |  |  | Tanks Up and Running | 1.5mo | Wed 1/31/29 | Mon 3/19/29 | 993994992 |  | Formula | Launch |  | Technical Scope | Formula |  | Del: FP
1078 | Execution | SNO | IOL |  |  | All sizes/All forms up and running | 0d | Thu 3/13/31 | Thu 3/13/31 | 1.0731e+19 | 1079 | Formula, package, Artwork | Launch |  | Technical Scope | Formula, package, Artwork |  | Del: FP
1079 | Execution | SNO | IOL |  |  | Inventory build (hard convert due to bottle sizes) | 60ed | Thu 3/13/31 | Mon 5/12/31 | 8338071078 | 1080SS+2mo | Formula, package, Artwork | Launch |  | Technical Scope | Formula, package, Artwork |  | Delivery
1080 | Execution | SNO | IOL |  |  | Ship to RDC | 3d | Wed 5/14/31 | Mon 5/19/31 | 1079SS+2mo | 1081 | Formula, package, Artwork | Launch |  | Technical Scope | Formula, package, Artwork |  | Delivery
1081 | Execution | SNO | IOL |  |  | SOS - Laundry | 1d | Mon 5/19/31 | Tue 5/20/31 | 1.0809e+21 | 29 | Formula, package, Artwork | Launch |  | Technical Scope | Formula, package, Artwork |  | Delivery