## Schedule
TaskId | Responsible Sub-team | Responsible Function | Task Name | Task Level | Predecessors IDs | Successors IDs | SCOPE | Learning_Plan | Critical
5 | All | IDM | Project Commitment (date projected) | L2 |  | 968 | SIMPL Gate | FALSE | FALSE
8 | All | IDM | LA Work Complete | L2 | 1017 |  | SIMPL Gate | FALSE | FALSE
21 | All | Sales | Initiative or Bundle Release to Trade (date needed) | L2 | 971 |  | SOS Dates | FALSE | FALSE
185 | Comm | Mktg | Initiative toolbox elements complete | L3 |  | 997 | Commercial Toolkit | FALSE | FALSE
252 | Comm | CMK | Claims Approved for Use | L7 |  | 979 | New Concept/Claims | TRUE | FALSE
313 | Comm | Mktg | Lock on Bds for Digimatics | L7 |  | 1000 | Commercial Toolkit | FALSE | FALSE
314 | Comm | Mktg | Print Plans | L7 |  | 1018 | Commercial Toolkit | FALSE | FALSE
315 | Comm | Mktg | Digital Plans | L7 |  | 1020 | Commercial Toolkit | FALSE | FALSE
316 | Comm | Mktg | In Store Plans | L7 |  | 1025 | Commercial Toolkit | FALSE | FALSE
317 | Comm | Mktg | Media Plans | L7 |  | 1028 | Commercial Toolkit | FALSE | FALSE
319 | Comm | Mktg | Approve Pre TableTop | L6 |  | 966 | Commercial Toolkit | FALSE | FALSE
569 | Comm | CMK | BASES II CMK Forecast Delivered (date expected) | L8 |  | 975 | New Package, New Formula | TRUE | FALSE
709 | Tech | PR | Approve BASES II results | L5 |  | 975 | New formula, blind change | TRUE | FALSE
710 | Tech | PR | Approve PC E&U results | L5 |  | 975 | New formula, blind change | TRUE | FALSE
711 | Tech | Formula | Complete formula definition for all non-consumer tested formulas (list variants) | L5 |  | 975 | New formula, blind change | FALSE | FALSE
722 | Comm | Mktg/ PR | Initial Approval of direction of Claims using success criteria | L5 |  | 967 | New formula, blind change | FALSE | FALSE
960 | Comm | Sales | Finalize GBP(field release) materials | L4 |  | 971 | Commercial Toolkit | FALSE | FALSE
965 | Comm | Mktg | LA/LPA Commercial Readiness | L2 |  | 966,967,968,969,970,971,973,974,993,997 | Commercial Toolkit | FALSE | TRUE
966 | Comm | Mktg | Updates Marketing Plans Based on Pre-Table Top | L3 | 319,965 | 1018,1028,994,995,996,969,1025,1000 | Commercial Toolkit | FALSE | TRUE
967 | Comm | Mktg | Legal concurrence of Mktg (final) MNI | L3 | 722,987,965 | 1018,1028,1025,1020,1000 | Commercial Toolkit | FALSE | TRUE
968 | Comm | CMK | TPA complete (to incl. trial plans) | L3 | 5,965 | 971,1328 | Commercial Toolkit | FALSE | TRUE
969 | Comm | Mktg | Leverage plan approved | L3 | 5,966,965 | 971 | Commercial Toolkit | FALSE | TRUE
970 | Comm | Mktg | Tabletop approved | L3 | 1018,1028,994,995,996,1026,1023,1022,1007,,1006,965 | 971,973,1328,997 | Commercial Toolkit | FALSE | TRUE
971 | Comm | Sales | MRAT Completed w/MDO | L3 | 970,960,968,969,965 | 21 | Commercial Toolkit | FALSE | TRUE
973 | Comm | CMK | Initiative tracker set-up | L3 | 970,965 | 1328 | Commercial Toolkit | FALSE | TRUE
974 | Comm | CMK | Final Proof of Claim (POC)/Claims Approval to Support all Mktg Elements | L3 | 965 | 975 | Commercial Toolkit | FALSE | TRUE
975 | Comm | PR | Product Available for R1 POCs (on-pack) | L4 | 569,709,710,711,,974 | 983 | Claims, concept | FALSE | FALSE
978 | Comm | Mktg | Claims Available | L5 | 975 | 979 | Claims, concept | FALSE | TRUE
979 | Comm | Mktg | R1 Claims Chosen | L6 | 252 | 983 | Claims, concept | FALSE | FALSE
983 | Comm | PR | POC testing R1 (all proposed) | L6 | 979,975 | 987 | Claims, concept | FALSE | FALSE
986 | Comm | Mktg | Claims reviewed/approved by legal | L5 | 975 | 987 | Claims, concept | FALSE | TRUE
987 | Comm | Mktg | Claim Legal Approval R1 | L6 | 983,1145 | 967,990,1171 | Claims, concept | FALSE | FALSE
990 | Comm | Mktg | Obtain NACS (Claim Number) R1 | L6 | 987 | 1060 | Claims, concept | FALSE | FALSE
993 | Comm | Mktg | 360 Mktg plan approved | L3 | 965 | 994 | Commercial Toolkit | FALSE | TRUE
994 | Comm | Mktg | Country XX | L4 | 966,993 | 1026,970 | Commercial Toolkit | FALSE | FALSE
995 | Comm | Mktg | Country XX | L4 | 966,993 | 1026,970 | Commercial Toolkit | FALSE | FALSE
996 | Comm | Mktg | Country XX | L4 | 966,993 | 1026,970 | Commercial Toolkit | FALSE | FALSE
997 | Comm | Mktg | Initiative toolbox elements complete | L3 | 185,970,965 | 1328 | Commercial Toolkit | FALSE | TRUE
998 | Comm | Mktg | TV Plans - Advertising Copy | L4 | 997 | 999 | Commercial Toolkit | FALSE | TRUE
999 | Comm | Mktg | Digimatic Production | L5 | 998 | 1000 | Commercial Toolkit | FALSE | TRUE
1000 | Comm | Mktg | Pre-Pro (award/pre-pro/dig production) | L6 | 5,319,966,967,313 | 1001 | Commercial Toolkit | FALSE | FALSE
1001 | Comm | Mktg | Round 1 Review | L6 | 1000 | 1002 | Commercial Toolkit | FALSE | FALSE
1002 | Comm | Mktg | Round 2 Review | L6 | 1001 | 1004 | Commercial Toolkit | FALSE | FALSE
1003 | Comm | Mktg | Digimatic Test #1 | L5 | 998 | 1004 | Commercial Toolkit | FALSE | TRUE
1004 | Comm | Mktg | In Field Testing (GM & USH) | L6 | 1002 | 1005 | Commercial Toolkit | FALSE | FALSE
1005 | Comm | Mktg | Test 1 Results | L6 | 1004 | 1006 | Commercial Toolkit | FALSE | FALSE
1006 | Comm | Mktg | Revisions | L6 | 1005 | 1007,970 | Commercial Toolkit | FALSE | FALSE
1007 | Comm | Mktg | Approve Final Direction for Full-up Production/GBP | L6 | 1006 | 970,1332,1333,1334 | Commercial Toolkit | FALSE | FALSE
1008 | Comm | Mktg | Full Up Production | L5 | 998 | 1009 | Commercial Toolkit | FALSE | TRUE
1009 | Comm | PR | PDD/Garment Brief Alignment | L6 | 313 | 1010 | Commercial Toolkit | FALSE | FALSE
1010 | Comm | PR | Conduct Garment Search | L6 | 1009 | 1011 | Commercial Toolkit | FALSE | FALSE
1011 | Comm | PR | Conduct Garment Test | L6 | 1010 | 1012 | Commercial Toolkit | FALSE | FALSE
1012 | Comm | Mktg | Pre-bid/Bid/Award | L6 | 313 | 1013 | Commercial Toolkit | FALSE | FALSE
1013 | Comm | Mktg | Prep/Scout/Cast/Set Design/Wardrobe | L6 | 1012 | 1014 | Commercial Toolkit | FALSE | FALSE
1014 | Comm | Mktg | Pre-pro Meeting/Shoot | L6 | 1013 | 1015 | Commercial Toolkit | FALSE | FALSE
1015 | Comm | Mktg | Edit/Agency Approvals/Revisions | L6 | 1014 | 1016 | Commercial Toolkit | FALSE | FALSE
1016 | Comm | Mktg | Present Rough Cuts | L6 | 1015 | 1017,1332,1333,1334 | Commercial Toolkit | FALSE | FALSE
1017 | Comm | Mktg | Approval/Finish (tie to field) | L6 | 1016 | 8 | Commercial Toolkit | FALSE | FALSE
1018 | Comm | Mktg | Print Plans | L5 | 314,319,966,967,998 | 970,1335 | Commercial Toolkit | FALSE | FALSE
1019 | Comm | Mktg | Digital Plans | L5 | 998 | 1020 | Commercial Toolkit | FALSE | TRUE
1020 | Comm | Mktg | Digital Objectives and Strategy | L6 | 315,319,967 | 1021 | Commercial Toolkit | FALSE | FALSE
1021 | Comm | Mktg | Menu of Executions (Websites, online ads, mobile ads etc.) | L6 | 1020 | 1022,1023 | Commercial Toolkit | FALSE | FALSE
1022 | Comm | Mktg | Search Guidelines | L6 | 1021 | 970 | Commercial Toolkit | FALSE | FALSE
1023 | Comm | Mktg | iMedia Guidelines | L6 | 1021 | 970,1337,1338,1339 | Commercial Toolkit | FALSE | FALSE
1024 | Comm | Mktg | In Store Plans | L5 | 998 | 1025 | Commercial Toolkit | FALSE | TRUE
1025 | Comm | CMK | InStore Plans Qualified | L6 | 316,319,966,967 | 1026 | Commercial Toolkit | FALSE | FALSE
1026 | Comm | Mktg | Confirm InStore Claims Are Approved by Legal | L6 | 994,1025 | 970,1027 | Commercial Toolkit | FALSE | FALSE
1027 | Comm | Mktg | In Store Plans Released for Retailer Engagement | L6 | 1026 | 1340 | Commercial Toolkit | FALSE | FALSE
1028 | Comm | Mktg | Media Plans | L5 | 317,319,966,967,998 | 970 | Commercial Toolkit | FALSE | FALSE
1033 | Supply | Design | Final Review- w/ GM- Approval | L5 |  | 1036 | New Artwork, Brand Arch | FALSE | FALSE
1034 | Supply | Design | DESIGN LOCK - Final Package to all Variants with Final Claims | L5 |  | 1057 | New Artwork, Brand Arch | FALSE | FALSE
1036 | Comm | Design | Agreed to Label/Primary Pack Design | L6 | 1033 | 1037 | New Artwork, Brand Arch | FALSE | FALSE
1037 | Comm | Design | Agreed to Test Substrates/SKUS/Finishes | L6 | 1036 | 1038 | New Artwork, Brand Arch | FALSE | FALSE
1038 | Comm | Design | Separations/Print Tools | L6 | 1037 | 1039 | New Artwork, Brand Arch | FALSE | FALSE
1039 | Comm | Design | Run new Labels/Bottles/Primary Pack | L6 | 1038 | 1040 | New Artwork, Brand Arch | FALSE | FALSE
1040 | Comm | Design | Final Approval of Locked Substrates and Finishes | L6 | 1039 | 1048,1057,,,, | New Artwork, Brand Arch | FALSE | FALSE
1046 | Supply | MPD | Provide TD in illustrator format to SGS (UC cap only new item), Approved TD | L6 |  | 1057 | New Artwork, Brand Arch | FALSE | FALSE
1048 | Supply | Design | Agency Upload GOS to Epadex | L7 | 1040 |  | New Artwork, Brand Arch | FALSE | FALSE
1049 | Supply | Mktg | Graphic Options Approval in Epadex (DCIC) | L7 |  | 1051 | New Artwork, Brand Arch | FALSE | FALSE
1051 | Comm | Artwork | Color development (assume 8 unique designs) | L7 | 1049, 1040 | 1053 | New Artwork, Brand Arch | FALSE | FALSE
1052 | Comm | Mktg | Master Copy Meeting- w/Legal - legal number for master copy | L7 | 1049, | 1053 | New Artwork, Brand Arch | FALSE | FALSE
1053 | Comm | Mktg | Master Copy approval - all waves (MF mtg) | L7 | 1051,1052 | 1054 | New Artwork, Brand Arch | FALSE | FALSE
1054 | Comm | Mktg | Upload Master Copy | L7 | 1053 | 1055 | New Artwork, Brand Arch | FALSE | FALSE
1055 | Supply | Artwork | Wave 1 - Approval | L7 | 1054 |  | New Artwork, Brand Arch | FALSE | FALSE
1057 | Comm | Design | Agency Upload GOS to Epadex | L7 | 1046,1034,1040,1048 | 1058, | New Artwork, Brand Arch | FALSE | FALSE
1058 | Comm | Mktg | Graphic Options Approval in Epadex (DCIC) | L7 | 1057 | 1061,1062, | New Artwork, Brand Arch | FALSE | FALSE
1060 | Comm | Artwork | Claim approval # needed (link to POC work) | L7 | 990, | 1061 | New Artwork, Brand Arch | FALSE | FALSE
1061 | Comm | Artwork | Color development (assume 20 unique designs) | L7 | 1058 | 1063 | New Artwork, Brand Arch | FALSE | FALSE
1062 | Comm | Mktg | Master Copy Meeting- w/Legal - legal number for master copy | L7 | 1058 | 1063 | New Artwork, Brand Arch | FALSE | FALSE
1063 | Comm | Mktg | Master Copy approval - all waves (MF mtg) | L7 | 1061,1062 | 1064 | New Artwork, Brand Arch | FALSE | FALSE
1064 | Comm | Mktg | Upload Master Copy | L7 | 1063 | 1065 | New Artwork, Brand Arch | FALSE | FALSE
1065 | Comm | Artwork | Wave 2 | L7 | 1064 | 1066,1161 | New Artwork, Brand Arch | FALSE | FALSE
1066 | Comm | Artwork | Wave 3 | L7 | 1065 | 1067,1161 | New Artwork, Brand Arch | FALSE | FALSE
1067 | Comm | Artwork | Wave 4 | L7 | 1066 | 1068,1161 | New Artwork, Brand Arch | FALSE | FALSE
1068 | Comm | Artwork | Wave 5 | L7 | 1067 | 1069,1161 | New Artwork, Brand Arch | FALSE | FALSE
1069 | Comm | Artwork | Wave 6 | L7 | 1068 | 1070,1161 | New Artwork, Brand Arch | FALSE | FALSE
1070 | Comm | Artwork | Wave 7 | L7 | 1069 | 1071,1161 | New Artwork, Brand Arch | FALSE | FALSE
1071 | Comm | Artwork | Wave 8 | L7 | 1070 | 1072,1161 | New Artwork, Brand Arch | FALSE | FALSE
1072 | Comm | Artwork | Wave 9 | L7 | 1071 | 1073,1161 | New Artwork, Brand Arch | FALSE | FALSE
1073 | Comm | Artwork | Wave 10 | L7 | 1072 | 1074,1161 | New Artwork, Brand Arch | FALSE | FALSE
1074 | Comm | Artwork | Wave 11 | L7 | 1073 | 1075,1161 | New Artwork, Brand Arch | FALSE | FALSE
1075 | Comm | Artwork | Wave 12 | L7 | 1074 | 1161 | New Artwork, Brand Arch | FALSE | FALSE
1145 | Tech | PD | POC template complete & approved | L4 |  | 987 | New package, new formula, eng scope, SND blind change | FALSE | FALSE
1161 | Tech | Pkg Dev | Primary Pack S&S (caps, wraps, labels, transitions, corrugate, etc) | L5 | 1065 |  | New Package, new formula, snd change, blind change | FALSE | FALSE
1171 | Tech | Process | Product QEC | L5 | 987 |  | New Package, new formula, snd change, blind change | FALSE | FALSE
1328 | All | IDM | Update Commercial LA documents | L5 | 968 |  | SIMPL Gate | FALSE | FALSE
1332 |  |  | Anthem approved | L4 | 1007 |  | Commercial Toolkit | FALSE | FALSE
1333 |  |  | USH Approved | L4 | 1007 |  | Commercial Toolkit | FALSE | FALSE
1334 |  |  | Copy Testing results | L4 | 1007 |  | Commercial Toolkit | FALSE | FALSE
1335 | Comm | Mktg | Print Execution | L3 | 1018 |  | Commercial Toolkit | FALSE | FALSE
1337 | Comm | Mktg | Digital Execution | L4 | 1023 |  | Commercial Toolkit | FALSE | FALSE
1338 | Comm | Mktg | Search Execution | L4 | 1023 |  | Commercial Toolkit | FALSE | FALSE
1339 | Comm | Mktg | iMedia Execution | L4 | 1023 |  | Commercial Toolkit | FALSE | FALSE
1340 | Comm | Mktg | In Store Execution | L3 | 1027 |  | Commercial Toolkit | FALSE | FALSE